## Sheet1
实物ID | 对象文本文本 | 技术对象类型 | 项目编码 | 项目描述 | WBS编码 | WBS描述 | 单体工程编码 | 单体工程描述 | 物资描述 | 供应商编码 | 物资组 | 物资号码 | 数量 | 工厂名称 | 供应商名称 | 设备标识(主设备:X) | 设备标识描述 | 工厂 | 写入日期 | 合同编号 | 电子商务合同行项目号 | 写入时间 | 采购结果序列号 | 招标计划编号 | 填报状态代码 | 填报状态描述 | 设备类型 | 设备类型描述 | 提报时间 | 库存地点 | 仓储地点的描述 | 批号 | 物资技术参数_工程ERP编码 | 物资技术参数_ERP工程名称 | 物资技术参数_对象文本文本 | 物资技术参数_技术对象类型 | 物资技术参数_单体工程编码 | 物资技术参数_单体工程描述 | 物资技术参数_物资提报状态 | 物资技术参数_物资技术参数 | 物资技术参数_网省编码 | 物资技术参数_提报日期 | 设备交接实验_工程ERP编码 | 设备交接实验_ERP工程名称 | 设备交接实验_单体工程编码 | 设备交接实验_单体工程描述 | 设备交接实验_记录名称 | 设备交接实验_设备类型编码 | 设备交接实验_设备类型名称 | 设备交接实验_试验性质 | 设备交接实验_负责人名称 | 设备交接实验_工作人员 | 设备交接实验_试验模板 | 设备交接实验_委托单位 | 设备交接实验_试验单位 | 设备交接实验_试验地点 | 设备交接实验_录入人id | 设备交接实验_录入人名称 | 设备交接实验_试验结论 | 设备交接实验_状态 | 设备交接实验_备注 | 设备交接实验_检修班组名称 | 设备交接实验_试验时间 | 设备交接实验_创建时间 | 设备安装调试_工程ERP编码 | 设备安装调试_ERP工程名称 | 设备安装调试_单体工程编码 | 设备安装调试_单体工程描述 | 设备安装调试_设备类型编码 | 设备安装调试_设备类型名称 | 设备安装调试_工作类型 | 设备安装调试_负责人名称 | 设备安装调试_工作人员 | 设备安装调试_录入人名称 | 设备安装调试_工作内容 | 设备安装调试_状态 | 设备安装调试_创建时间 | 设备名称 | 电压等级 | 原始描述 | 参数数量 | 标准电压等级 | 技术参数_额定电压 | 技术参数_型号 | 技术参数_生产厂家 | 技术参数_结构形式 | 技术参数_出厂编号 | 技术参数_解析错误
016010000000000026873174 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 17021099 | G1020001 | 500031353 | 9 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 2 | 163229 | 1 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:33:20 | 91AR |  | 1901058672 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-420/1046","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202106Y01882-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:33:20 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[202106Y01882-3]-电气-交接-2021-08-01 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-01 00:00:00 | 2021-12-30 13:52:54 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变500kV母避雷器C相，设备质量无异常 | 归档 | 2021-12-27 16:05:05 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-420/1046 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202106Y01882-3
016010000000000026873181 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 17021099 | G1020001 | 500031353 | 9 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 2 | 163229 | 2 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058672 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202106Y01881-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[202106Y01881-3]-电气-交接-2021-08-01 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-01 00:00:00 | 2021-12-30 13:41:18 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变500kV母避雷器A相，设备质量无异常 | 归档 | 2021-12-27 16:03:53 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202106Y01881-3
016010000000000026873198 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 17021099 | G1020001 | 500031353 | 9 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 2 | 163229 | 3 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058672 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202106Y01880-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[202106Y01880-3]-电气-交接-2021-08-01 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-01 00:00:00 | 2021-12-30 13:48:27 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变500kV母避雷器B相，设备质量无异常 | 归档 | 2021-12-27 16:04:31 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202106Y01880-3
016010000000000026873204 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 17021099 | G1020001 | 500031353 | 9 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 2 | 163229 | 4 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058672 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02020-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 16:03:01 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5043避雷器C相，设备质量无异常 | 归档 | 2021-12-27 15:59:03 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02020-3
016010000000000026873211 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 17021099 | G1020001 | 500031353 | 9 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 2 | 163229 | 5 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058672 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02019-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 16:26:05 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5053避雷器B相，设备质量无异常 | 归档 | 2021-12-27 16:00:21 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02019-3
016010000000000026873228 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 17021099 | G1020001 | 500031353 | 9 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 2 | 163229 | 6 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058672 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02018-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 15:53:49 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5043避雷器A相，设备质量无异常 | 归档 | 2021-12-27 15:57:55 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02018-3
016010000000000026873235 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 17021099 | G1020001 | 500031353 | 9 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 2 | 163229 | 7 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058672 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02017-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强 刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 10:37:44 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5013避雷器A相，设备质量无异常 | 归档 | 2021-12-27 15:52:55 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02017-3
016010000000000026873242 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 17021099 | G1020001 | 500031353 | 9 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 2 | 163229 | 8 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058672 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02016-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 15:57:06 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5043避雷器B相，设备质量无异常 | 归档 | 2021-12-27 15:58:30 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02016-3
016010000000000026873259 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 17021099 | G1020001 | 500031353 | 9 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 2 | 163229 | 9 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058672 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02015-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 16:17:37 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5053避雷器A相，设备质量无异常 | 归档 | 2021-12-27 15:59:38 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,420kV,瓷,1046kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02015-3
016010000000000026873266 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 1 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02014-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 11:49:41 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5013避雷器C相，设备质量无异常 | 归档 | 2021-12-27 15:55:22 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02014-3
016010000000000026873273 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 2 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02013-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 11:56:22 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5031避雷器B相，设备质量无异常 | 归档 | 2021-12-27 15:56:34 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02013-3
016010000000000026873280 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 3 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02012-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 11:53:13 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5031避雷器A相，设备质量无异常 | 归档 | 2021-12-27 15:56:00 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02012-3
016010000000000026873297 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 4 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02011-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 16:29:17 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5053避雷器C相，设备质量无异常 | 归档 | 2021-12-27 16:01:06 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02011-3
016010000000000026873303 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 5 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02010-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 11:59:02 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5031避雷器C相，设备质量无异常 | 归档 | 2021-12-27 15:57:13 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02010-3
016010000000000026873310 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 6 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-444/1106","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02009-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 六氟化硫气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强 刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-27 11:20:00 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5013避雷器B相，设备质量无异常 | 归档 | 2021-12-27 15:53:34 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-444/1106 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02009-3
016010000000000026873327 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 7 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-420/1046","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02008-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[202103Y02008-3]-电气-交接-2021-08-01 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-01 00:00:00 | 2021-12-30 13:36:42 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变500kV母避雷器C相，设备质量无异常 | 归档 | 2021-12-27 16:03:17 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-420/1046 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02008-3
016010000000000026873334 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 8 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-420/1046","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02007-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-28 09:43:47 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变500kV侧5041避雷器C相，设备质量无异常 | 归档 | 2021-12-27 16:06:49 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-420/1046 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02007-3
016010000000000026873341 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 9 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-420/1046","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02006-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[202103Y02006-3]-电气-交接-2021-08-01 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-01 00:00:00 | 2021-12-30 13:26:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变500kV母避雷器A相，设备质量无异常 | 归档 | 2021-12-27 16:01:54 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-420/1046 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02006-3
016010000000000026873358 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 10 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-420/1046","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02005-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[202103Y02005-3]-电气-交接-2021-08-01 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-01 00:00:00 | 2021-12-30 13:31:55 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变500kV母避雷器B相，设备质量无异常 | 归档 | 2021-12-27 16:02:41 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-420/1046 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02005-3
016010000000000026873365 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 11 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-420/1046","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02001-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-28 09:41:03 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变500kV侧5041避雷器B相，设备质量无异常 | 归档 | 2021-12-27 16:06:15 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-420/1046 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02001-3
016010000000000026873372 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17021099 | G1020001 | 500031354 | 12 | 国网湖南电力集中采购工厂 | 厦门ABB避雷器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000085 | 1 | 163229 | 12 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-07-08 15:30:07 | 91AR |  | 1901058671 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210625","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"","ZLCKDY":"","MXJS":"3","ZZGJMC":"","SCCJ":"007341","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"420","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1046","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20WZ-420/1046","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"","BCFDDL":"20","CCBH":"202103Y02000-3","EDPL":"50","SCCJMC":"厦门ABB避雷器有限公司","CXYXDY":""} | 41311046430000000 | 2021-07-08 15:30:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 318 | 避雷器 | 交接 |  | 王志强，刘政 | 48169B50-8185-42BB-8941-A09EEEC9601F-00278 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 编辑中 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-28 09:36:50 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变500kV侧5041避雷器A相，设备质量无异常 | 归档 | 2021-12-27 16:05:41 | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 420kV | Y20WZ-420/1046 | 厦门ABB避雷器有限公司 | 金属氧化物 | 202103Y02000-3
016010000000000026872153 | 电缆终端 | 1100000033 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449686 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV电缆终端,3×240,户外终端,冷缩,铜 | 17016449 | G1408001 | 500021169 | 2 | 国网湖南电力集中采购工厂 | 吉林省中科电缆附件有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000039 | 1 | 163130 | 1 | SG2003 | [5 empty] | 91AR |  | 1901097602 | [32 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 202 | 电缆终端 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 35kV电缆终端安装，设备质量无异常 | 归档 | 2021-12-28 10:12:39 | 35kV电缆终端 | 3×240 | 35kV电缆终端,3×240,户外终端,冷缩,铜 | 5 | 3×240
016010000000000026872160 | 电缆终端 | 1100000033 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449686 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV电缆终端,3×240,户外终端,冷缩,铜 | 17016449 | G1408001 | 500021169 | 2 | 国网湖南电力集中采购工厂 | 吉林省中科电缆附件有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000039 | 1 | 163130 | 2 | SG2003 | [5 empty] | 91AR |  | 1901097602 | [32 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 202 | 电缆终端 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 电缆终端安装，设备质量无异常 | 归档 | 2021-12-28 10:13:49 | 35kV电缆终端 | 3×240 | 35kV电缆终端,3×240,户外终端,冷缩,铜 | 5 | 3×240
016010000000000024840963 | 柱上断路器 | 1601000013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 柱上断路器,AC10kV,630A,20kA,真空,无隔离闸刀,户外 | 17003751 | G1008003 | 500001036 | 1 | 国网湖南电力集中采购工厂 | 国电南瑞南京控制系统有限公司 | X | 主设备 | 1000 | 20200513 |  | 0 | 152023 | 1 | 1620PW04 | 1 | 已提报 | 柱上负荷开关 | 柱上负荷开关 | 2020-10-14 10:53:38 | 91AR |  | 1901003021 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 柱上负荷开关 | S16001005 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZW20-12/T630','SCCJMC':'国电南瑞南京控制系统有限公司','SCCJ':'002325','CCBH':'NR2005200001','CCRQ':'20200817','MHJZMC':'真空','MHJZ':'02','CZFSMC':'电动','CZFS':'02','JDDZ':'10.0000','EDDY':'12','EDDL':'630.0000','ZDKDDL':'20000.0000'} | 41311046430000000 | 2020-10-14 10:53:38 | [35 empty] | 柱上断路器 | AC10kV | 柱上断路器,AC10kV,630A,20kA,真空,无隔离闸刀,户外 | 7 | 10kV | [5 empty] | 无效JSON格式
016010000000000026871644 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 1 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21076","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21076]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 15:01:44 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安向线608避雷器A相，设备质量无异常 | 归档 | 2021-12-27 15:43:04 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21076
016010000000000026871651 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 2 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21077","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21077]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 15:27:13 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安玉线644避雷器C相，设备质量无异常 | 归档 | 2021-12-27 15:47:09 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21077
016010000000000026871668 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 3 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21078","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21078]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 15:41:58 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安玉线646避雷器A相，设备质量无异常 | 归档 | 2021-12-27 15:47:48 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21078
016010000000000026871675 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 4 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21079","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21079]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500KV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 16:07:41 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变220kV侧630避雷器B相，设备质量无异常 | 归档 | 2021-12-27 15:50:56 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21079
016010000000000026871682 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 5 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21080","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21080]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 14:42:03 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安通线634避雷器B相，设备质量无异常 | 归档 | 2021-12-27 15:41:23 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21080
016010000000000026871699 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 6 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21081","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21081]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 13:51:04 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安楚线618避雷器C相安装，设备质量无异常 | 归档 | 2021-12-27 15:35:32 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21081
016010000000000026871705 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 7 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21082","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21082]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 14:06:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安楚线622避雷器B相，设备质量无异常 | 归档 | 2021-12-27 15:38:21 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21082
016010000000000026871712 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 8 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21083","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21083]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 15:48:05 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安玉线646避雷器B相，设备质量无异常 | 归档 | 2021-12-27 15:48:33 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21083
016010000000000026871729 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 9 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21084","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21084]-电气-交接- | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 14:37:06 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安通线634避雷器A相，设备质量无异常 | 归档 | 2021-12-27 15:40:14 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21084
016010000000000026871736 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 10 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21085","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21085]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 15:09:49 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安向线608避雷器B相，设备质量无异常 | 归档 | 2021-12-27 15:43:48 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21085
016010000000000026871743 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 11 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21086","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21086]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500KV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 15:51:20 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安玉线646避雷器C相，设备质量无异常 | 归档 | 2021-12-27 15:49:32 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21086
016010000000000026871750 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 12 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21087","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21087]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 14:02:14 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安楚线622避雷器A相安装，设备质量无异常 | 归档 | 2021-12-27 15:37:17 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21087
016010000000000026871767 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 13 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21088","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21088]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 15:18:29 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安玉线644避雷器A相，设备质量无异常 | 归档 | 2021-12-27 15:45:18 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21088
016010000000000026871774 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 14 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21089","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21089]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 14:49:37 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安通线634避雷器C相，设备质量无异常 | 归档 | 2021-12-27 15:42:13 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21089
016010000000000026871781 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 15 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21090","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21090]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 15:14:08 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安向线608避雷器C相，设备质量无异常 | 归档 | 2021-12-27 15:44:29 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21090
016010000000000026871798 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 16 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21091","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21091]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500KV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 16:11:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变220kV侧630避雷器C相，设备质量无异常 | 归档 | 2021-12-27 15:51:41 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21091
016010000000000026871804 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 17 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21092","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21092]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500KV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 15:59:26 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变220kV侧630避雷器A相，设备质量无异常 | 归档 | 2021-12-27 15:50:07 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21092
016010000000000026871811 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 18 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21093","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21093]-电气-交接-2021-12-01 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-12-01 00:00:00 | 2021-12-27 13:05:01 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安楚线618避雷器A相安装，设备质量无异常 | 归档 | 2021-12-27 10:26:03 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21093
016010000000000026871828 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 19 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21094","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21094]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 15:22:48 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安玉线644避雷器B相，设备质量无异常 | 归档 | 2021-12-27 15:46:00 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21094
016010000000000026871835 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 20 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21095","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21095]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 14:10:18 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安楚线622避雷器C相，设备质量无异常 | 归档 | 2021-12-27 15:39:18 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21095
016010000000000026871842 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 17005615 | G1020001 | 500027164 | 21 | 国网湖南电力集中采购工厂 | 宁波市镇海国创高压电器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000084 | 1 | 162540 | 21 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-30 15:07:07 | 91AR |  | 1901058633 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"FDJXLXMC":"普通阀式","FDJXLX":"2","CPDH":"","EDPL":"50.0000","MXJS":"2.0000","QDLCSZYXDY":"700.0000","JYDZCSZ":"20000.0000","JSQXH":"JCQ1","SFDJXMC":"无间隙","SFDJX":"1","JGXSMC":"金属氧化物","JGXS":"1","CZCJDLXCY":"452.0000","ZXDLCSZYXDY":"110.0000","DDLCJDLZ":"100.0000","DXFBCJDLZ":"600.0000","YLSFDL":"50.0000","FBTLRL":"600.0000","GPCKDY":"204.0000","GD":"3488.0000","JSQSCCJ":"宁波市镇海国创高压电器有限公司","EDDY":"204","SCCJMC":"宁波市镇海国创高压电器有限公司","SCCJ":"005729","CCBH":"G21096","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210628","XH":"Y10WZ-204/532","JYTLXMC":"瓷外套","JYTLX":"1","CXYXDY":"159.0000","GPFDDY":"0.0000","BCFDDL":"10.0000","LDCJCYFZ":"532.0000","PDBJ":"31.0000","ZLCKDY":"296.0000","YWJYHMC":"有","YWJYH":"1","DBCJDLXCY":"594.0000","CXYXDL":"1.2000"} | 41311046430000000 | 2021-06-30 15:07:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-避雷器[G21096]-电气-交接-2021-07-27 | 318 | 避雷器 | 交接 |  | 匡成，文轩 | 31E8FA48D32C905CA05E30F3F3015E31E8F9D400E4 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 宁乡 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-27 00:00:00 | 2021-12-27 13:43:01 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安楚线618避雷器B相安装，设备质量无异常 | 归档 | 2021-12-27 10:43:45 | 交流避雷器 | AC220kV | 交流避雷器,AC220kV,204kV,瓷,532kV,不带间隙 | 6 | 220kV | 204kV | Y10WZ-204/532 | 宁波市镇海国创高压电器有限公司 | 金属氧化物 | G21096
016010000000000026872221 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,100/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500111989 | 3 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 1 | 163130 | 1 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119399 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"100.0000","EDPL":"50.0000","EDDLB":"100/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 |  |  |  |  | 文轩 |  | 编辑中 |  | 电气试验三队 | 2021-07-24 19:20:02 | 2021-12-27 19:20:02 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变2站用变432电流互感器A相，设备质量无异常 | 归档 | 2021-12-27 16:07:20 | 35kV油浸电磁CT | 100/1 | 35kV油浸电磁CT,100/1,0.5,5P,3,15,倒立 | 7 | 100/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872238 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,100/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500111989 | 3 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 1 | 163130 | 2 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119399 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"100.0000","EDPL":"50.0000","EDDLB":"100/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 11:12:37 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变2站用变432电流互感器B相，设备质量无异常 | 归档 | 2021-12-27 16:07:53 | 35kV油浸电磁CT | 100/1 | 35kV油浸电磁CT,100/1,0.5,5P,3,15,倒立 | 7 | 100/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872245 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,100/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500111989 | 3 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 1 | 163130 | 3 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119399 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"100.0000","EDPL":"50.0000","EDDLB":"100/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 11:27:24 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变2站用变432电流互感器C相，设备质量无异常 | 归档 | 2021-12-27 16:08:24 | 35kV油浸电磁CT | 100/1 | 35kV油浸电磁CT,100/1,0.5,5P,3,15,倒立 | 7 | 100/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872252 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 1 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 17:06:26 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变2C电容器438电流互感器C相，设备质量无异常 | 归档 | 2021-12-27 16:13:21 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872269 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 2 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 20:01:25 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3C电容器446电流互感器B相，设备质量无异常 | 归档 | 2021-12-27 16:14:52 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872276 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 3 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 17:22:53 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变3C电容器446电流互感器A相，设备质量无异常 | 归档 | 2021-12-27 16:14:00 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872283 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 4 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 11:43:15 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变1C电容器434电流互感器A相，设备质量无异常 | 归档 | 2021-12-27 16:08:55 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872290 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 5 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 11:59:19 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变1C电容器434电流互感器B相，设备质量无异常 | 归档 | 2021-12-27 16:09:35 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872306 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 6 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 14:15:41 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变2C电容器438电流互感器A相，设备质量无异常 | 归档 | 2021-12-27 16:11:55 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872313 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 7 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 14:50:31 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变2C电容器438电流互感器B相，设备质量无异常 | 归档 | 2021-12-27 16:12:38 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872320 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 8 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 20:16:42 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3C电容器446电流互感器C相，设备质量无异常 | 归档 | 2021-12-27 16:15:36 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872337 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 9 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 13:23:24 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变1C电容器434电流互感器C相，设备质量无异常 | 归档 | 2021-12-27 16:10:29 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872344 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 10 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 20:40:47 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变融冰444电流互感器B相，设备质量无异常 | 归档 | 2021-12-27 16:17:23 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872351 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 11 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 21:04:19 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变融冰444电流互感器C相，设备质量无异常 | 归档 | 2021-12-27 16:17:56 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872368 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 18007251 | G1003001 | 500115035 | 12 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 2 | 163130 | 12 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119400 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVB-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"2500.0000","EDPL":"50.0000","EDDLB":"2500/1","CLBB":"","BHBB":"","ECRZZSL":"3.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 20:29:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变融冰444电流互感器A相，设备质量无异常 | 归档 | 2021-12-27 16:16:40 | 35kV油浸电磁CT | 1600/1 | 35kV油浸电磁CT,1600/1,0.5,5P,3,15,倒立 | 7 | 1600/1 | 35kV | LVB-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872375 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449665 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,2×2000/1,无测量级,TPY,5,15,倒立 | 18007251 | G1003001 | 500137367 | 3 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 3 | 163130 | 1 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119401 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVBT-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"4000.0000","EDPL":"50.0000","EDDLB":"2*2000/1","CLBB":"","BHBB":"","ECRZZSL":"5.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-25 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-25 00:00:00 | 2021-12-29 11:28:48 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变35kV侧430电流互感器B相，设备质量无异常 | 归档 | 2021-12-27 16:19:00 | 35kV油浸电磁CT | 2×2000/1 | 35kV油浸电磁CT,2×2000/1,无测量级,TPY,5,15,倒立 | 7 | 2×2000/1 | 35kV | LVBT-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872382 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449665 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,2×2000/1,无测量级,TPY,5,15,倒立 | 18007251 | G1003001 | 500137367 | 3 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 3 | 163130 | 2 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119401 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVBT-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"4000.0000","EDPL":"50.0000","EDDLB":"2*2000/1","CLBB":"","BHBB":"","ECRZZSL":"5.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 20:49:56 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变35kV侧430电流互感器C相，设备质量无异常 | 归档 | 2021-12-27 16:19:31 | 35kV油浸电磁CT | 2×2000/1 | 35kV油浸电磁CT,2×2000/1,无测量级,TPY,5,15,倒立 | 7 | 2×2000/1 | 35kV | LVBT-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026872399 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449665 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸电磁CT,2×2000/1,无测量级,TPY,5,15,倒立 | 18007251 | G1003001 | 500137367 | 3 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000086 | 3 | 163130 | 3 | SG2003 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2021-08-04 10:17:38 | 91AR |  | 1901119401 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"LVBT-35","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","CCRQ":"20210507","JGXSMC":"倒立式","JGXS":"2","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JYLXMC":"油纸电容型","JYLX":"01","ECXHSCXSMC":"","ECXHSCXS":"","YCCGQYLMC":"","YCCGQYL":"","MFXSMC":"","MFXS":"","YH":"","SF6QTEDYL":"","SF6QTZXYXYL":"","SF6QTBJYL":"","SF6QTZL":"","SF6QTYSYL":"","YZ":"","YCJ":"","GD":"","ZZ":"","CPXH":"","EDDY":"35","EDDL":"4000.0000","EDPL":"50.0000","EDDLB":"2*2000/1","CLBB":"","BHBB":"","ECRZZSL":"5.0000","JYSP":"","ECRZSLCL":"","ECRZSLBH":"","ECRZSLZTBH":"","ZQJCL":"","ZQJBH":"","ZQJZTBH":"","EDSCRLCL":"","EDSCRLBH":"","EDSCRLZTBH":"","BMJYDYDJ":"","EDYCDL":"","EDKDYCDLXS":"","EDDSRDL":"","EDECSC":"","EDSYSJ":"","FZDY":"","YXBB":"","DWDDL":"100.0000","RWDDL":"40.0000","PDBJ":"","LXRWDDL":"","RWDDLSJ":"","ZDCXDL":"","LDCJDY":"","CZCJDY":"","DSNSDL":"","PDJL":"","ZDCXDY":"","LDCJNYFZ":"","DSRDL":"","CZCJNYFZST":"","ZLNY":"","KSZTDL":"","JBFDSYDY":"","ZLDLCLJD":"","WXDGRSYDY":"","XBDLCLJD":"","JYXY1090":"","BZ":""} | 41311046430000000 | 2021-08-04 10:17:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电流互感器[ ]-电气-交接-2021-07-24 | 313 | 电流互感器 | 交接 |  | 匡成，文轩 | 5B0A723E692C905CA05E5A358E015E5B0A714201F6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-24 00:00:00 | 2021-12-28 21:18:32 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 313 | 电流互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变35kV侧430电流互感器A相，设备质量无异常 | 归档 | 2021-12-27 16:18:29 | 35kV油浸电磁CT | 2×2000/1 | 35kV油浸电磁CT,2×2000/1,无测量级,TPY,5,15,倒立 | 7 | 2×2000/1 | 35kV | LVBT-35 | 泰开集团山东泰开互感器有限公司 | 倒立式
016010000000000026881490 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605465 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 18007251 | G1005002 | 500139712 | 6 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000613 | 1 | 164752 | 1 | SG2005 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2021-09-14 10:48:52 | 91AR |  | 1901121941 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"TYD500/√3-0.005H","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"TYD500/√3-0.005H","ZZGJMC":"","ZZGJ":"","CCRQ":"20210806","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JGXSMC":"电容式","JGXS":"2","TXJGMC":"","TXJG":"","ECXHSCXSMC":"","ECXHSCXS":"","DRQJS":"","YH":"","SF6QTEDYL":"","SF6QTBJYL":"","SJDRQBH":"","SJDRQXS":"","ZJDRQBH":"","ZJDRQXS":"","XJC1DRQBH":"","XJC1DRQXS":"","XJC2DRQBH":"","XJC2DRQXS":"","YCJ":"","YZ":"","SF6QTZL":"","LXMC":"","LX":"","EDDY":"500","EDPL":"50.0000","EDDYB":"500/√3：0.1/√3：0.1/√3：0.1/√3：0.1kV","CLBB":"","BHBB":"","ECRZZSL":"4.0000","PDBJ":"","ZEDDRL":"","ECRZSLCL":"","ECRZSLBH":"","MFJGMC":"","MFJG":"","JYSP":"","ZZ":"1500.0000","GD":"","EDKLZJDY":"","ZQJCL":"","ZQJBH":"","EDSCRLCL":"","EDSCRLBH":"","SJDRL":"","ZJDRL":"","XJC1DRL":"","XJC2DRL":"","SCFYB":"","BZ":""} | 41311046430000000 | 2021-09-14 10:48:52 | [35 empty] | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | 500kV | TYD500/√3-0.005H | 泰开集团山东泰开互感器有限公司 | 电容式
016010000000000026881506 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605465 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 18007251 | G1005002 | 500139712 | 6 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000613 | 1 | 164752 | 2 | SG2005 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2021-09-14 10:48:52 | 91AR |  | 1901121941 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"TYD500/√3-0.005H","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"TYD500/√3-0.005H","ZZGJMC":"","ZZGJ":"","CCRQ":"20210806","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JGXSMC":"电容式","JGXS":"2","TXJGMC":"","TXJG":"","ECXHSCXSMC":"","ECXHSCXS":"","DRQJS":"","YH":"","SF6QTEDYL":"","SF6QTBJYL":"","SJDRQBH":"","SJDRQXS":"","ZJDRQBH":"","ZJDRQXS":"","XJC1DRQBH":"","XJC1DRQXS":"","XJC2DRQBH":"","XJC2DRQXS":"","YCJ":"","YZ":"","SF6QTZL":"","LXMC":"","LX":"","EDDY":"500","EDPL":"50.0000","EDDYB":"500/√3：0.1/√3：0.1/√3：0.1/√3：0.1kV","CLBB":"","BHBB":"","ECRZZSL":"4.0000","PDBJ":"","ZEDDRL":"","ECRZSLCL":"","ECRZSLBH":"","MFJGMC":"","MFJG":"","JYSP":"","ZZ":"1500.0000","GD":"","EDKLZJDY":"","ZQJCL":"","ZQJBH":"","EDSCRLCL":"","EDSCRLBH":"","SJDRL":"","ZJDRL":"","XJC1DRL":"","XJC2DRL":"","SCFYB":"","BZ":""} | 41311046430000000 | 2021-09-14 10:48:52 | [35 empty] | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | 500kV | TYD500/√3-0.005H | 泰开集团山东泰开互感器有限公司 | 电容式
016010000000000026881513 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605465 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 18007251 | G1005002 | 500139712 | 6 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000613 | 1 | 164752 | 3 | SG2005 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2021-09-14 10:48:52 | 91AR |  | 1901121941 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"TYD500/√3-0.005H","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"TYD500/√3-0.005H","ZZGJMC":"","ZZGJ":"","CCRQ":"20210806","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JGXSMC":"电容式","JGXS":"2","TXJGMC":"","TXJG":"","ECXHSCXSMC":"","ECXHSCXS":"","DRQJS":"","YH":"","SF6QTEDYL":"","SF6QTBJYL":"","SJDRQBH":"","SJDRQXS":"","ZJDRQBH":"","ZJDRQXS":"","XJC1DRQBH":"","XJC1DRQXS":"","XJC2DRQBH":"","XJC2DRQXS":"","YCJ":"","YZ":"","SF6QTZL":"","LXMC":"","LX":"","EDDY":"500","EDPL":"50.0000","EDDYB":"500/√3：0.1/√3：0.1/√3：0.1/√3：0.1kV","CLBB":"","BHBB":"","ECRZZSL":"4.0000","PDBJ":"","ZEDDRL":"","ECRZSLCL":"","ECRZSLBH":"","MFJGMC":"","MFJG":"","JYSP":"","ZZ":"1500.0000","GD":"","EDKLZJDY":"","ZQJCL":"","ZQJBH":"","EDSCRLCL":"","EDSCRLBH":"","SJDRL":"","ZJDRL":"","XJC1DRL":"","XJC2DRL":"","SCFYB":"","BZ":""} | 41311046430000000 | 2021-09-14 10:48:52 | [35 empty] | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | 500kV | TYD500/√3-0.005H | 泰开集团山东泰开互感器有限公司 | 电容式
016010000000000026881520 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605465 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 18007251 | G1005002 | 500139712 | 6 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000613 | 1 | 164752 | 4 | SG2005 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2021-09-14 10:48:52 | 91AR |  | 1901121941 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"TYD500/√3-0.005H","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"TYD500/√3-0.005H","ZZGJMC":"","ZZGJ":"","CCRQ":"20210806","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JGXSMC":"电容式","JGXS":"2","TXJGMC":"","TXJG":"","ECXHSCXSMC":"","ECXHSCXS":"","DRQJS":"","YH":"","SF6QTEDYL":"","SF6QTBJYL":"","SJDRQBH":"","SJDRQXS":"","ZJDRQBH":"","ZJDRQXS":"","XJC1DRQBH":"","XJC1DRQXS":"","XJC2DRQBH":"","XJC2DRQXS":"","YCJ":"","YZ":"","SF6QTZL":"","LXMC":"","LX":"","EDDY":"500","EDPL":"50.0000","EDDYB":"500/√3：0.1/√3：0.1/√3：0.1/√3：0.1kV","CLBB":"","BHBB":"","ECRZZSL":"4.0000","PDBJ":"","ZEDDRL":"","ECRZSLCL":"","ECRZSLBH":"","MFJGMC":"","MFJG":"","JYSP":"","ZZ":"1500.0000","GD":"","EDKLZJDY":"","ZQJCL":"","ZQJBH":"","EDSCRLCL":"","EDSCRLBH":"","SJDRL":"","ZJDRL":"","XJC1DRL":"","XJC2DRL":"","SCFYB":"","BZ":""} | 41311046430000000 | 2021-09-14 10:48:52 | [35 empty] | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | 500kV | TYD500/√3-0.005H | 泰开集团山东泰开互感器有限公司 | 电容式
016010000000000026881537 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605465 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 18007251 | G1005002 | 500139712 | 6 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000613 | 1 | 164752 | 5 | SG2005 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2021-09-14 10:48:52 | 91AR |  | 1901121941 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"TYD500/√3-0.005H","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"TYD500/√3-0.005H","ZZGJMC":"","ZZGJ":"","CCRQ":"20210806","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JGXSMC":"电容式","JGXS":"2","TXJGMC":"","TXJG":"","ECXHSCXSMC":"","ECXHSCXS":"","DRQJS":"","YH":"","SF6QTEDYL":"","SF6QTBJYL":"","SJDRQBH":"","SJDRQXS":"","ZJDRQBH":"","ZJDRQXS":"","XJC1DRQBH":"","XJC1DRQXS":"","XJC2DRQBH":"","XJC2DRQXS":"","YCJ":"","YZ":"","SF6QTZL":"","LXMC":"","LX":"","EDDY":"500","EDPL":"50.0000","EDDYB":"500/√3：0.1/√3：0.1/√3：0.1/√3：0.1kV","CLBB":"","BHBB":"","ECRZZSL":"4.0000","PDBJ":"","ZEDDRL":"","ECRZSLCL":"","ECRZSLBH":"","MFJGMC":"","MFJG":"","JYSP":"","ZZ":"1500.0000","GD":"","EDKLZJDY":"","ZQJCL":"","ZQJBH":"","EDSCRLCL":"","EDSCRLBH":"","SJDRL":"","ZJDRL":"","XJC1DRL":"","XJC2DRL":"","SCFYB":"","BZ":""} | 41311046430000000 | 2021-09-14 10:48:52 | [35 empty] | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | 500kV | TYD500/√3-0.005H | 泰开集团山东泰开互感器有限公司 | 电容式
016010000000000026881544 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605465 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 18007251 | G1005002 | 500139712 | 6 | 国网湖南电力集中采购工厂 | 山东泰开互感器有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000613 | 1 | 164752 | 6 | SG2005 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2021-09-14 10:48:52 | 91AR |  | 1901121941 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"TYD500/√3-0.005H","SCCJMC":"泰开集团山东泰开互感器有限公司","SCCJ":"015424","CCBH":" ","CPDH":"TYD500/√3-0.005H","ZZGJMC":"","ZZGJ":"","CCRQ":"20210806","JYJZMC":"油浸","JYJZ":"1","WJYXSMC":"瓷质","WJYXS":"1","JGXSMC":"电容式","JGXS":"2","TXJGMC":"","TXJG":"","ECXHSCXSMC":"","ECXHSCXS":"","DRQJS":"","YH":"","SF6QTEDYL":"","SF6QTBJYL":"","SJDRQBH":"","SJDRQXS":"","ZJDRQBH":"","ZJDRQXS":"","XJC1DRQBH":"","XJC1DRQXS":"","XJC2DRQBH":"","XJC2DRQXS":"","YCJ":"","YZ":"","SF6QTZL":"","LXMC":"","LX":"","EDDY":"500","EDPL":"50.0000","EDDYB":"500/√3：0.1/√3：0.1/√3：0.1/√3：0.1kV","CLBB":"","BHBB":"","ECRZZSL":"4.0000","PDBJ":"","ZEDDRL":"","ECRZSLCL":"","ECRZSLBH":"","MFJGMC":"","MFJG":"","JYSP":"","ZZ":"1500.0000","GD":"","EDKLZJDY":"","ZQJCL":"","ZQJBH":"","EDSCRLCL":"","EDSCRLBH":"","SJDRL":"","ZJDRL":"","XJC1DRL":"","XJC2DRL":"","SCFYB":"","BZ":""} | 41311046430000000 | 2021-09-14 10:48:52 | [35 empty] | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | 500kV | TYD500/√3-0.005H | 泰开集团山东泰开互感器有限公司 | 电容式
016010000000000026871859 | 配电变压器 | 160200001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449682 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 10kV变压器,800kVA,普通,硅钢片,油浸 | 17002546 | G1001002 | 500007447 | 1 | 国网湖南电力集中采购工厂 | 常州东芝变压器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000092 | 2 | 163130 | 1 | SG2003 | [5 empty] | 91AR |  | 1901072725 | [32 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 110 | 柱上变压器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变0站用变安装，设备质量无异常 | 归档 | 2021-12-28 10:03:56 | 10kV变压器 | 800kVA | 10kV变压器,800kVA,普通,硅钢片,油浸 | 5 | 800kV
016010000000000026872412 | 主变压器 | 140100001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449680 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV油浸有载变压器,800kVA,35/0.4,一体 | 17002546 | G1001004 | 500004787 | 1 | 国网湖南电力集中采购工厂 | 常州东芝变压器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000092 | 1 | 163130 | 1 | SG2003 | [5 empty] | 91AR |  | 1901072726 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-主变压器[]-电气-交接-2021-09-24 | 301 | 主变压器 | 交接 |  | 匡成，文轩 | 6E99AEFF292C905CA05E6E64B7015E6E99AE9B00C6 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-09-24 00:00:00 | 2022-01-04 11:35:19 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 301 | 主变压器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变2站用变安装，设备质量无异常 | 归档 | 2021-12-28 10:04:31 | 35kV油浸有载变压器 | 800kVA | 35kV油浸有载变压器,800kVA,35/0.4,一体 | 4 | 800kV
016010000000000026872467 | 主变压器 | 140100001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449631 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kV单相油浸无励磁自耦变压器,334MVA,500/220/35,一体 | 17002546 | G1001009 | 500000805 | 3 | 国网湖南电力集中采购工厂 | 常州东芝变压器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000092 | 3 | 163130 | 1 | SG2003 | 1 | 已提报 | 主变压器 | 主变压器 | 2021-03-24 10:53:36 | 91AR |  | 1901056530 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 主变压器 | 140100001 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"ODFS-334000/500","SCCJMC":"常州东芝变压器有限公司","SCCJ":"001215","CCBH":"C2021008","CCRQ":"20210201","CPDH":"X1593A","ZZGJMC":"中国","ZZGJ":"CN","JYNRDJMC":"A","JYNRDJ":"1","FWDJMC":"","FWDJ":"","ZZ":"245.0000","YH":"25","YZ":"62.0000","YCD":"克拉玛依","SF6QTEDYL":"","SF6QTBJYL":"","QSZ":"123.0000","YSZ":"150.0000","YZRL":"","YZMFFSMC":"胶囊式","YZMFFS":"4","YWRHXMC":"","YWRHX":"","SJYXZ":"19.0000","YQXJGMC":"","YQXJG":"","SF6CJ":"","SF6QTZL":"","SF6QZBT":"","SF6QZDLC":"","SF6QZYZKG":"","SF6QTYLBT":"","SF6QTYLDLC":"","SF6QTYLYZKG":"","LQSZ":"","EDDY":"525.0000","EDDL":"1102.0000","EDPL":"50.0000","JYJZMC":"油浸","JYJZ":"1","RZXSMC":"自耦","RZXS":"3","JGXSMC":"芯式","JGXS":"1","LQFSMC":"自然油循环风冷(ONAF)","LQFS":"2","DYFSMC":"无励磁调压","DYFS":"2","LJZBH":"YNa0d11","EDRL":"334.0000","RLB":"334/334/100","ZLQRL":"234.0000","EDDYZY":"230.0000","EDDYDY":"36.0000","EDDLZY":"2515.0000","EDDLDY":"2778.0000","JYSP":"680/1550/1175","JYSPZXD":"140/325","QPFLZS":"70.0000","DYB":"525/230/36","FZSHGYDY":"151.5000","FZSHGYZY":"434.8000","FZSHZYDY":"154.3000","DLZKGYZY":"17.6400","DLZKGYDY":"59.2500","DLZKZYDY":"38.1800","KZDL":"0.0300","KZSH":"69.0000","FZSHMZ":"434.8000","ZSSP":"70.0000"} | 41311046430000000 | 2021-03-24 10:53:36 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-主变压器[C2021008]-电气-交接-2021-10-09 | 301 | 主变压器 | 交接 |  | 丁义，王策勇，邹晨乔，王涛，傅刚，何光乐，向缨竹，罗鹏飞 | 64810A85172C905CA05E645350015E648109D80158 | 国家电网有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 吴文兵 | 合格 | 编辑中 |  | 湘电设备评价所 | 2021-10-09 00:00:00 | 2021-12-25 13:38:32 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 301 | 主变压器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变3主变A相安装，设备质量无异常 | 归档 | 2021-12-28 10:02:15 | 500kV单相油浸无励磁自耦变压器 | 334MVA | 500kV单相油浸无励磁自耦变压器,334MVA,500/220/35,一体 | 4 | 334MVA | 525.0000kV | ODFS-334000/500 | 常州东芝变压器有限公司 | 芯式 | C2021008
016010000000000026872474 | 主变压器 | 140100001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449631 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kV单相油浸无励磁自耦变压器,334MVA,500/220/35,一体 | 17002546 | G1001009 | 500000805 | 3 | 国网湖南电力集中采购工厂 | 常州东芝变压器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000092 | 3 | 163130 | 2 | SG2003 | 1 | 已提报 | 主变压器 | 主变压器 | 2021-03-24 10:47:23 | 91AR |  | 1901056530 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 主变压器 | 140100001 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"ODFS-334000/500","SCCJMC":"常州东芝变压器有限公司","SCCJ":"001215","CCBH":"C2021009","CCRQ":"20210201","CPDH":"X1593B","ZZGJMC":"中国","ZZGJ":"CN","JYNRDJMC":"A","JYNRDJ":"1","FWDJMC":"","FWDJ":"","ZZ":"245.0000","YH":"25","YZ":"62.0000","YCD":"克拉玛依","SF6QTEDYL":"","SF6QTBJYL":"","QSZ":"123.0000","YSZ":"150.0000","YZRL":"","YZMFFSMC":"胶囊式","YZMFFS":"4","YWRHXMC":"","YWRHX":"","SJYXZ":"19.0000","YQXJGMC":"","YQXJG":"","SF6CJ":"","SF6QTZL":"","SF6QZBT":"","SF6QZDLC":"","SF6QZYZKG":"","SF6QTYLBT":"","SF6QTYLDLC":"","SF6QTYLYZKG":"","LQSZ":"","EDDY":"525.0000","EDDL":"1102.0000","EDPL":"50.0000","JYJZMC":"油浸","JYJZ":"1","RZXSMC":"自耦","RZXS":"3","JGXSMC":"芯式","JGXS":"1","LQFSMC":"自然油循环风冷(ONAF)","LQFS":"2","DYFSMC":"无励磁调压","DYFS":"2","LJZBH":"YNa0d11","EDRL":"334.0000","RLB":"334/334/100","ZLQRL":"234.0000","EDDYZY":"230.0000","EDDYDY":"36.0000","EDDLZY":"2515.0000","EDDLDY":"2778.0000","JYSP":"680/1550/1175","JYSPZXD":"140/325","QPFLZS":"70.0000","DYB":"525/230/36","FZSHGYDY":"151.1000","FZSHGYZY":"429.2000","FZSHZYDY":"155.2000","DLZKGYZY":"17.8900","DLZKGYDY":"59.2900","DLZKZYDY":"37.9700","KZDL":"0.0300","KZSH":"69.8000","FZSHMZ":"429.2000","ZSSP":"70.0000"} | 41311046430000000 | 2021-03-24 10:47:23 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-主变压器[C2021009]-电气-交接-2021-10-09 | 301 | 主变压器 | 交接 |  | 丁义，王策勇，邹晨乔，王涛，傅刚，何光乐，向缨竹，罗鹏飞 | A2D1F54B-F6B9-4261-BB10-424BD75CB156-13887 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 王策勇 | 合格 | 归档 |  | 设备评价所 | 2021-10-09 00:00:00 | 2021-12-25 15:37:54 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 301 | 主变压器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变3主变B相安装，设备质量无异常 | 归档 | 2021-12-28 10:02:47 | 500kV单相油浸无励磁自耦变压器 | 334MVA | 500kV单相油浸无励磁自耦变压器,334MVA,500/220/35,一体 | 4 | 334MVA | 525.0000kV | ODFS-334000/500 | 常州东芝变压器有限公司 | 芯式 | C2021009
016010000000000026872481 | 主变压器 | 140100001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449631 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kV单相油浸无励磁自耦变压器,334MVA,500/220/35,一体 | 17002546 | G1001009 | 500000805 | 3 | 国网湖南电力集中采购工厂 | 常州东芝变压器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000092 | 3 | 163130 | 3 | SG2003 | 1 | 已提报 | 主变压器 | 主变压器 | 2021-03-24 10:33:28 | 91AR |  | 1901056530 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 主变压器 | 140100001 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"ODFS-334000/500","SCCJMC":"常州东芝变压器有限公司","SCCJ":"001215","CCBH":"C2021010","CCRQ":"20210303","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","JYNRDJMC":"A","JYNRDJ":"1","FWDJMC":"","FWDJ":"","ZZ":"3.8900","YH":"25","YZ":"62.0000","YCD":"克拉玛依","SF6QTEDYL":"","SF6QTBJYL":"","QSZ":"123.0000","YSZ":"150.0000","YZRL":"","YZMFFSMC":"胶囊式","YZMFFS":"4","YWRHXMC":"","YWRHX":"","SJYXZ":"19.0000","YQXJGMC":"","YQXJG":"","SF6CJ":"","SF6QTZL":"","SF6QZBT":"","SF6QZDLC":"","SF6QZYZKG":"","SF6QTYLBT":"","SF6QTYLDLC":"","SF6QTYLYZKG":"","LQSZ":"","EDDY":"525.0000","EDDL":"1102.0000","EDPL":"50.0000","JYJZMC":"油浸","JYJZ":"1","RZXSMC":"自耦","RZXS":"3","JGXSMC":"芯式","JGXS":"1","LQFSMC":"自然油循环风冷(ONAF)","LQFS":"2","DYFSMC":"无励磁调压","DYFS":"2","LJZBH":"YNa0d11","EDRL":"334.0000","RLB":"334/334/100","ZLQRL":"234.0000","EDDYZY":"230.0000","EDDYDY":"36.0000","EDDLZY":"2515.0000","EDDLDY":"2778.0000","JYSP":"680/1550/1175","JYSPZXD":"140/325","QPFLZS":"70.0000","DYB":"525/230/36","FZSHGYDY":"153.4000","FZSHGYZY":"432.3000","FZSHZYDY":"149.2000","DLZKGYZY":"17.8900","DLZKGYDY":"59.3300","DLZKZYDY":"38.1100","KZDL":"0.0300","KZSH":"69.8000","FZSHMZ":"432.3000","ZSSP":"70.0000"} | 41311046430000000 | 2021-03-24 10:33:28 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-主变压器[C2021010]-电气-交接-2021-10-09 | 301 | 主变压器 | 交接 |  | 丁义，王策勇，邹晨乔，王涛，傅刚，何光乐，向缨竹，罗鹏飞 | A2D1F54B-F6B9-4261-BB10-424BD75CB156-13887 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 王策勇 | 合格 | 归档 |  | 设备评价所 | 2021-10-09 00:00:00 | 2021-12-25 15:43:35 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 301 | 主变压器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变3主变C相安装，设备质量无异常 | 归档 | 2021-12-28 10:03:21 | 500kV单相油浸无励磁自耦变压器 | 334MVA | 500kV单相油浸无励磁自耦变压器,334MVA,500/220/35,一体 | 4 | 334MVA | 525.0000kV | ODFS-334000/500 | 常州东芝变压器有限公司 | 芯式 | C2021010
016010000000000026873143 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC35kV,51kV,瓷,134kV,不带间隙 | 17004151 | G1020001 | 500004652 | 3 | 国网湖南电力集中采购工厂 | 恒大电气有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000083 | 1 | 163229 | 1 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-16 10:39:39 | 91AR |  | 1901058591 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210611","DDLCJDLZ":"65","GPCKDY":"51","ZZGJ":"CN","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"1","ZLCKDY":"73","MXJS":"1","ZZGJMC":"中国","SCCJ":"043117","FDJXLXMC":"","FBTLRL":"400","JSQSCCJ":"南阳高新区天成电气设备有限公司","EDDY":"51","CZCJDLXCY":"114","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"JCQ-3E","LDCJCYFZ":"134","DBCJDLXCY":"154","SFDJX":"1","YWJYHMC":"无","CPDH":"","XH":"Y5WZ-51/134","JYDZCSZ":"","YWJYH":"0","ZXDLCSZYXDY":"","JYTLXMC":"瓷外套","BCFDDL":"5","CCBH":"21030555","EDPL":"50","SCCJMC":"恒大电气有限公司","CXYXDY":"40.8"} | 41311046430000000 | 2021-06-16 10:39:39 | [22 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变3主变35kV侧避雷器A相安装，设备质量无异常 | 归档 | 2021-12-28 10:07:54 | 交流避雷器 | AC35kV | 交流避雷器,AC35kV,51kV,瓷,134kV,不带间隙 | 6 | 35kV | 51kV | Y5WZ-51/134 | 恒大电气有限公司 | 金属氧化物 | 21030555
016010000000000026873150 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC35kV,51kV,瓷,134kV,不带间隙 | 17004151 | G1020001 | 500004652 | 3 | 国网湖南电力集中采购工厂 | 恒大电气有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000083 | 1 | 163229 | 2 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-16 10:39:39 | 91AR |  | 1901058591 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210611","DDLCJDLZ":"65","GPCKDY":"51","ZZGJ":"CN","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"1","ZLCKDY":"73","MXJS":"1","ZZGJMC":"中国","SCCJ":"043117","FDJXLXMC":"","FBTLRL":"400","JSQSCCJ":"南阳高新区天成电气设备有限公司","EDDY":"51","CZCJDLXCY":"114","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"JCQ-3E","LDCJCYFZ":"134","DBCJDLXCY":"154","SFDJX":"1","YWJYHMC":"无","CPDH":"","XH":"Y5WZ-51/134","JYDZCSZ":"","YWJYH":"0","ZXDLCSZYXDY":"","JYTLXMC":"瓷外套","BCFDDL":"5","CCBH":"21030556","EDPL":"50","SCCJMC":"恒大电气有限公司","CXYXDY":"40.8"} | 41311046430000000 | 2021-06-16 10:39:39 | [22 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变3主变35kV侧避雷器B相安装，设备质量无异常 | 归档 | 2021-12-28 10:08:49 | 交流避雷器 | AC35kV | 交流避雷器,AC35kV,51kV,瓷,134kV,不带间隙 | 6 | 35kV | 51kV | Y5WZ-51/134 | 恒大电气有限公司 | 金属氧化物 | 21030556
016010000000000026873167 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449655 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC35kV,51kV,瓷,134kV,不带间隙 | 17004151 | G1020001 | 500004652 | 3 | 国网湖南电力集中采购工厂 | 恒大电气有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000083 | 1 | 163229 | 3 | SG2003 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-06-16 10:39:39 | 91AR |  | 1901058591 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20210611","DDLCJDLZ":"65","GPCKDY":"51","ZZGJ":"CN","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"1","ZLCKDY":"73","MXJS":"1","ZZGJMC":"中国","SCCJ":"043117","FDJXLXMC":"","FBTLRL":"400","JSQSCCJ":"南阳高新区天成电气设备有限公司","EDDY":"51","CZCJDLXCY":"114","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"JCQ-3E","LDCJCYFZ":"134","DBCJDLXCY":"154","SFDJX":"1","YWJYHMC":"无","CPDH":"","XH":"Y5WZ-51/134","JYDZCSZ":"","YWJYH":"0","ZXDLCSZYXDY":"","JYTLXMC":"瓷外套","BCFDDL":"5","CCBH":"21030557","EDPL":"50","SCCJMC":"恒大电气有限公司","CXYXDY":"40.8"} | 41311046430000000 | 2021-06-16 10:39:39 | [22 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 318 | 避雷器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变3主变35kV侧避雷器C相安装，设备质量无异常 | 归档 | 2021-12-28 10:09:41 | 交流避雷器 | AC35kV | 交流避雷器,AC35kV,51kV,瓷,134kV,不带间隙 | 6 | 35kV | 51kV | Y5WZ-51/134 | 恒大电气有限公司 | 金属氧化物 | 21030557
016010000000000026884224 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605467 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17000053 | G1020001 | 500031354 | 6 | 国网湖南电力集中采购工厂 | 抚顺电瓷制造有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000600 | 1 | 165202 | 1 | SG2005 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-10-19 15:01:54 | 91AR |  | 1901097784 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20201127","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"CN","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"1","ZLCKDY":"","MXJS":"3","ZZGJMC":"中国","SCCJ":"001948","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"444","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1106","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20W1-444/1106W","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"瓷外套","BCFDDL":"20","CCBH":"03821","EDPL":"50","SCCJMC":"抚顺电瓷制造有限公司","CXYXDY":""} | 41311046430000000 | 2021-10-19 15:01:54 | [35 empty] | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 444kV | Y20W1-444/1106W | 抚顺电瓷制造有限公司 | 金属氧化物 | 03821
016010000000000026884231 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605467 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17000053 | G1020001 | 500031354 | 6 | 国网湖南电力集中采购工厂 | 抚顺电瓷制造有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000600 | 1 | 165202 | 2 | SG2005 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-10-19 15:01:54 | 91AR |  | 1901097784 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20201127","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"CN","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"1","ZLCKDY":"","MXJS":"3","ZZGJMC":"中国","SCCJ":"001948","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"444","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1106","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20W1-444/1106W","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"瓷外套","BCFDDL":"20","CCBH":"03822","EDPL":"50","SCCJMC":"抚顺电瓷制造有限公司","CXYXDY":""} | 41311046430000000 | 2021-10-19 15:01:54 | [35 empty] | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 444kV | Y20W1-444/1106W | 抚顺电瓷制造有限公司 | 金属氧化物 | 03822
016010000000000026884248 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605467 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17000053 | G1020001 | 500031354 | 6 | 国网湖南电力集中采购工厂 | 抚顺电瓷制造有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000600 | 1 | 165202 | 3 | SG2005 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-10-19 15:01:54 | 91AR |  | 1901097784 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20201127","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"CN","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"1","ZLCKDY":"","MXJS":"3","ZZGJMC":"中国","SCCJ":"001948","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"444","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1106","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20W1-444/1106W","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"瓷外套","BCFDDL":"20","CCBH":"03823","EDPL":"50","SCCJMC":"抚顺电瓷制造有限公司","CXYXDY":""} | 41311046430000000 | 2021-10-19 15:01:54 | [35 empty] | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 444kV | Y20W1-444/1106W | 抚顺电瓷制造有限公司 | 金属氧化物 | 03823
016010000000000026884255 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605467 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17000053 | G1020001 | 500031354 | 6 | 国网湖南电力集中采购工厂 | 抚顺电瓷制造有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000600 | 1 | 165202 | 4 | SG2005 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-10-19 15:01:54 | 91AR |  | 1901097784 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20201127","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"CN","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"1","ZLCKDY":"","MXJS":"3","ZZGJMC":"中国","SCCJ":"001948","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"444","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1106","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20W1-444/1106W","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"瓷外套","BCFDDL":"20","CCBH":"03824","EDPL":"50","SCCJMC":"抚顺电瓷制造有限公司","CXYXDY":""} | 41311046430000000 | 2021-10-19 15:01:54 | [35 empty] | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 444kV | Y20W1-444/1106W | 抚顺电瓷制造有限公司 | 金属氧化物 | 03824
016010000000000026884262 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605467 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17000053 | G1020001 | 500031354 | 6 | 国网湖南电力集中采购工厂 | 抚顺电瓷制造有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000600 | 1 | 165202 | 5 | SG2005 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-10-19 15:01:54 | 91AR |  | 1901097784 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20201127","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"CN","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"1","ZLCKDY":"","MXJS":"3","ZZGJMC":"中国","SCCJ":"001948","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"444","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1106","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20W1-444/1106W","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"瓷外套","BCFDDL":"20","CCBH":"03969","EDPL":"50","SCCJMC":"抚顺电瓷制造有限公司","CXYXDY":""} | 41311046430000000 | 2021-10-19 15:01:54 | [35 empty] | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 444kV | Y20W1-444/1106W | 抚顺电瓷制造有限公司 | 金属氧化物 | 03969
016010000000000026884279 | 避雷器 | 140300024 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605467 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 17000053 | G1020001 | 500031354 | 6 | 国网湖南电力集中采购工厂 | 抚顺电瓷制造有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000600 | 1 | 165202 | 6 | SG2005 | 1 | 已提报 | 避雷器(变电) | 避雷器(变电) | 2021-10-19 15:01:54 | 91AR |  | 1901097784 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 避雷器(变电) | 140300024 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"DXFBCJDLZ":"","CCRQ":"20201127","DDLCJDLZ":"","GPCKDY":"","ZZGJ":"CN","CXYXDL":"","FDJXLX":"","SFDJXMC":"无间隙","GPFDDY":"","JYTLX":"1","ZLCKDY":"","MXJS":"3","ZZGJMC":"中国","SCCJ":"001948","FDJXLXMC":"","FBTLRL":"","JSQSCCJ":"","EDDY":"444","CZCJDLXCY":"","JGXSMC":"金属氧化物","PDBJ":"31","JGXS":"1","YLSFDL":"","GD":"","QDLCSZYXDY":"","JSQXH":"","LDCJCYFZ":"1106","DBCJDLXCY":"","SFDJX":"1","YWJYHMC":"","CPDH":"","XH":"Y20W1-444/1106W","JYDZCSZ":"","YWJYH":"","ZXDLCSZYXDY":"","JYTLXMC":"瓷外套","BCFDDL":"20","CCBH":"03970","EDPL":"50","SCCJMC":"抚顺电瓷制造有限公司","CXYXDY":""} | 41311046430000000 | 2021-10-19 15:01:54 | [35 empty] | 交流避雷器 | AC500kV | 交流避雷器,AC500kV,444kV,瓷,1106kV,不带间隙 | 6 | 500kV | 444kV | Y20W1-444/1106W | 抚顺电瓷制造有限公司 | 金属氧化物 | 03970
016010000000000026879855 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605461 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVHGIS组合电器,63kA,1CB,5000A,户外 | 17036521 | G1015002 | 500115229 | 1 | 国网湖南电力集中采购工厂 | 新东北电气集团高压开关有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000581 | 1 | 164150 | 1 | SG2005 | [5 empty] | 91AR |  | 1901118796 | [45 empty] | 500kVHGIS组合电器 | 63kA | 500kVHGIS组合电器,63kA,1CB,5000A,户外 | 5 | 63kV
016010000000000026879862 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605463 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVHGIS组合电器,63kA,2CB,5000A,户外 | 17036521 | G1015002 | 500074972 | 1 | 国网湖南电力集中采购工厂 | 新东北电气集团高压开关有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000581 | 2 | 164150 | 1 | SG2005 | [5 empty] | 91AR |  | 1901004172 | [45 empty] | 500kVHGIS组合电器 | 63kA | 500kVHGIS组合电器,63kA,2CB,5000A,户外 | 5 | 63kV
016010000000000026872177 | 电力电容器 | 140300010 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449670 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV框架式电容器组（不含电抗器）,60000kvar,500kvar | 17000082 | G1017006 | 500050977 | 1 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 4 | 163130 | 1 | SG2003 | 1 | 已提报 | 电力电容器 | 电力电容器 | 2021-03-26 14:04:38 | 91AR |  | 1901073596 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电力电容器 | 140300010 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"TBB35-60000/500-AQW","SCCJMC":"日新电机（无锡）有限公司","SCCJ":"006114","CCBH":"202010026","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","TS":"120.0000","ZZRL":"60000.0000","EDDY":"35","EDDL":"833.3000","EDPL":"50.0000","JYJZMC":"油浸","JYJZ":"1","DRQZNBBHFSMC":"","DRQZNBBHFS":"","DTBHFSMC":"内熔丝","DTBHFS":"1","DTRL":"500.0000","DRZ":"44.2100"} | 41311046430000000 | 2021-03-26 14:04:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电力电容器[202010026]-电气-交接-2021-08-30 | 316 | 电力电容器 | 交接 |  | 匡成，文轩 | 4F939686992C905CA05E4F9396015E4F9396850000 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-30 00:00:00 | 2021-12-29 13:59:21 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 316 | 电力电容器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变1C电容器安装，设备质量无异常 | 归档 | 2021-12-27 16:22:51 | 35kV框架式电容器组（不含电抗器） | 60000kvar | 35kV框架式电容器组（不含电抗器）,60000kvar,500kvar | 3 | 60000kV | 35kV | TBB35-60000/500-AQW | 日新电机（无锡）有限公司 |  | 202010026
016010000000000026872184 | 电力电容器 | 140300010 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449668 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV框架式电容器组（不含电抗器）,60000kvar,500kvar | 17000082 | G1017006 | 500050977 | 2 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 1 | 163130 | 1 | SG2003 | 1 | 已提报 | 电力电容器 | 电力电容器 | 2021-03-26 14:02:27 | 91AR |  | 1901073599 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电力电容器 | 140300010 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"TBB35-60000/500-AQW","SCCJMC":"日新电机（无锡）有限公司","SCCJ":"006114","CCBH":"202010025","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","TS":"120.0000","ZZRL":"60000.0000","EDDY":"35","EDDL":"833.3000","EDPL":"50.0000","JYJZMC":"油浸","JYJZ":"1","DRQZNBBHFSMC":"","DRQZNBBHFS":"","DTBHFSMC":"内熔丝","DTBHFS":"1","DTRL":"500.0000","DRZ":"44.2100"} | 41311046430000000 | 2021-03-26 14:02:27 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电力电容器[202010025]-电气-交接-2021-08-30 | 316 | 电力电容器 | 交接 |  | 匡成，文轩 | 4F939686992C905CA05E4F9396015E4F9396850000 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-30 00:00:00 | 2021-12-29 14:03:07 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 316 | 电力电容器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变2C电容器安装，设备质量无异常 | 归档 | 2021-12-27 16:27:32 | 35kV框架式电容器组（不含电抗器） | 60000kvar | 35kV框架式电容器组（不含电抗器）,60000kvar,500kvar | 3 | 60000kV | 35kV | TBB35-60000/500-AQW | 日新电机（无锡）有限公司 |  | 202010025
016010000000000026872191 | 电力电容器 | 140300010 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449668 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV框架式电容器组（不含电抗器）,60000kvar,500kvar | 17000082 | G1017006 | 500050977 | 2 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 1 | 163130 | 2 | SG2003 | 1 | 已提报 | 电力电容器 | 电力电容器 | 2021-03-26 13:58:27 | 91AR |  | 1901073599 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电力电容器 | 140300010 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"TBB35-60000/500-AQW","SCCJMC":"日新电机（无锡）有限公司","SCCJ":"006114","CCBH":"202010024","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","TS":"120.0000","ZZRL":"60000.0000","EDDY":"35","EDDL":"909.1000","EDPL":"50.0000","JYJZMC":"油浸","JYJZ":"1","DRQZNBBHFSMC":"","DRQZNBBHFS":"","DTBHFSMC":"内熔丝","DTBHFS":"1","DTRL":"500.0000","DRZ":"52.6100"} | 41311046430000000 | 2021-03-26 13:58:27 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电力电容器[202010024]-电气-交接-2021-10-01 | 316 | 电力电容器 | 交接 |  | 匡成，文轩 | 4F939686992C905CA05E4F9396015E4F9396850000 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-30 00:00:00 | 2021-12-29 13:23:22 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 316 | 电力电容器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3C电容器安装，设备质量无异常 | 归档 | 2021-12-27 16:46:04 | 35kV框架式电容器组（不含电抗器） | 60000kvar | 35kV框架式电容器组（不含电抗器）,60000kvar,500kvar | 3 | 60000kV | 35kV | TBB35-60000/500-AQW | 日新电机（无锡）有限公司 |  | 202010024
016010000000000026872702 | 电抗器 | 140300005 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449676 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 17000082 | G1012012 | 500123851 | 6 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 2 | 163158 | 1 | SG2003 | 1 | 已提报 | 电抗器-一般变电站 | 电抗器-一般变电站 | 2021-03-30 15:07:13 | 91AR |  | 1901073598 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电抗器-一般变电站 | 140300005 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"CKGKL-35-2400/2.88-12%","SCCJMC":"天津经纬正能电气设备有限公司","SCCJ":"043352","CCBH":"JWZN210022JWZN210023","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","LQFSMC":"自然空气冷却(AN)","LQFS":"8","DYFSMC":"无调压","DYFS":"3","ZZ":"2.3900","YH":"","YCD":"","QSZ":"","YZ":"","YXJGMC":"","YXJG":"","YZMFFSMC":"","YZMFFS":"","JYNRDJMC":"","JYNRDJ":"","FWDJMC":"","FWDJ":"","EDDY":"35","EDDL":"832.9000","EDPL":"50.0000","JYJZMC":"环氧树脂","JYJZ":"4","DCJGMC":"空芯","DCJG":"1","EDRL":"2400.0000","EDDK":"3.4600","EDDKL":"12.0000","EDDG":"11.0140","EDSH":"27.6000","BFZK":"","EDDSNSDL":"","EDFZNSDL":"","EDDLCXSJ":"","JYSP":"","JYSPZXD":"","LXDK":"","LXYXDGDYBS":"","LXYXDGDLBS":""} | 41311046430000000 | 2021-03-30 15:07:13 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电抗器[JWZN210022JWZN210023]-电气-交接-2021-08-22 | 312 | 电抗器 | 交接 |  | 匡成，文轩 | E8675C23612C905C965FE66F2D015FE8675A3103E1 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-22 00:00:00 | 2021-12-29 15:47:11 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 312 | 电抗器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变2C电容器438串联电抗器A相安装，设备质量无异常 | 归档 | 2021-12-27 16:44:23 | 电容器组串联电抗器 | AC35kV | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 5 | 35kV | 35kV | CKGKL-35-2400/2.88-12% | 天津经纬正能电气设备有限公司 |  | JWZN210022JWZN210023
016010000000000026872719 | 电抗器 | 140300005 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449676 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 17000082 | G1012012 | 500123851 | 6 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 2 | 163158 | 2 | SG2003 | 1 | 已提报 | 电抗器-一般变电站 | 电抗器-一般变电站 | 2021-03-30 15:07:48 | 91AR |  | 1901073598 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电抗器-一般变电站 | 140300005 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"CKGKL-35-2400/2.88-12%","SCCJMC":"天津经纬正能电气设备有限公司","SCCJ":"043352","CCBH":"JWZN210022JWZN210023","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","LQFSMC":"自然空气冷却(AN)","LQFS":"8","DYFSMC":"无调压","DYFS":"3","ZZ":"2.3900","YH":"","YCD":"","QSZ":"","YZ":"","YXJGMC":"","YXJG":"","YZMFFSMC":"","YZMFFS":"","JYNRDJMC":"","JYNRDJ":"","FWDJMC":"","FWDJ":"","EDDY":"35","EDDL":"832.9000","EDPL":"50.0000","JYJZMC":"环氧树脂","JYJZ":"4","DCJGMC":"空芯","DCJG":"1","EDRL":"2400.0000","EDDK":"3.4600","EDDKL":"12.0000","EDDG":"11.0140","EDSH":"27.6000","BFZK":"","EDDSNSDL":"","EDFZNSDL":"","EDDLCXSJ":"","JYSP":"","JYSPZXD":"","LXDK":"","LXYXDGDYBS":"","LXYXDGDLBS":""} | 41311046430000000 | 2021-03-30 15:07:48 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电抗器[JWZN210022JWZN210023]-电气-交接-2021-08-22 | 312 | 电抗器 | 交接 |  | 匡成，文轩 | E8675C23612C905C965FE66F2D015FE8675A3103E1 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-22 00:00:00 | 2021-12-29 15:53:02 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 312 | 电抗器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变2C电容器438串联电抗器B相安装，设备质量无异常 | 归档 | 2021-12-27 16:45:02 | 电容器组串联电抗器 | AC35kV | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 5 | 35kV | 35kV | CKGKL-35-2400/2.88-12% | 天津经纬正能电气设备有限公司 |  | JWZN210022JWZN210023
016010000000000026872726 | 电抗器 | 140300005 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449676 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 17000082 | G1012012 | 500123851 | 6 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 2 | 163158 | 3 | SG2003 | 1 | 已提报 | 电抗器-一般变电站 | 电抗器-一般变电站 | 2021-03-30 15:08:12 | 91AR |  | 1901073598 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电抗器-一般变电站 | 140300005 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"CKGKL-35-2400/2.88-12%","SCCJMC":"天津经纬正能电气设备有限公司","SCCJ":"043352","CCBH":"JWZN210022JWZN210023","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","LQFSMC":"自然空气冷却(AN)","LQFS":"8","DYFSMC":"无调压","DYFS":"3","ZZ":"2.3900","YH":"","YCD":"","QSZ":"","YZ":"","YXJGMC":"","YXJG":"","YZMFFSMC":"","YZMFFS":"","JYNRDJMC":"","JYNRDJ":"","FWDJMC":"","FWDJ":"","EDDY":"35","EDDL":"832.9000","EDPL":"50.0000","JYJZMC":"环氧树脂","JYJZ":"4","DCJGMC":"空芯","DCJG":"1","EDRL":"2400.0000","EDDK":"3.4600","EDDKL":"12.0000","EDDG":"11.0140","EDSH":"27.6000","BFZK":"","EDDSNSDL":"","EDFZNSDL":"","EDDLCXSJ":"","JYSP":"","JYSPZXD":"","LXDK":"","LXYXDGDYBS":"","LXYXDGDLBS":""} | 41311046430000000 | 2021-03-30 15:08:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电抗器[JWZN210022JWZN210023]-电气-交接-2021-08-22 | 312 | 电抗器 | 交接 |  | 匡成，文轩 | E8675C23612C905C965FE66F2D015FE8675A3103E1 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-22 00:00:00 | 2021-12-29 15:59:30 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 312 | 电抗器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变2C电容器438串联电抗器C相安装，设备质量无异常 | 归档 | 2021-12-27 16:45:33 | 电容器组串联电抗器 | AC35kV | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 5 | 35kV | 35kV | CKGKL-35-2400/2.88-12% | 天津经纬正能电气设备有限公司 |  | JWZN210022JWZN210023
016010000000000026872733 | 电抗器 | 140300005 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449676 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 17000082 | G1012012 | 500123851 | 6 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 2 | 163158 | 4 | SG2003 | 1 | 已提报 | 电抗器-一般变电站 | 电抗器-一般变电站 | 2021-03-30 15:08:45 | 91AR |  | 1901073598 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电抗器-一般变电站 | 140300005 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"CKGKL-35-2400/2.88-12%","SCCJMC":"天津经纬正能电气设备有限公司","SCCJ":"043352","CCBH":"JWZN210022JWZN210023","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","LQFSMC":"自然空气冷却(AN)","LQFS":"8","DYFSMC":"无调压","DYFS":"3","ZZ":"2.3900","YH":"","YCD":"","QSZ":"","YZ":"","YXJGMC":"","YXJG":"","YZMFFSMC":"","YZMFFS":"","JYNRDJMC":"","JYNRDJ":"","FWDJMC":"","FWDJ":"","EDDY":"35","EDDL":"832.9000","EDPL":"50.0000","JYJZMC":"环氧树脂","JYJZ":"4","DCJGMC":"空芯","DCJG":"1","EDRL":"2400.0000","EDDK":"3.4600","EDDKL":"12.0000","EDDG":"11.0140","EDSH":"27.6000","BFZK":"","EDDSNSDL":"","EDFZNSDL":"","EDDLCXSJ":"","JYSP":"","JYSPZXD":"","LXDK":"","LXYXDGDYBS":"","LXYXDGDLBS":""} | 41311046430000000 | 2021-03-30 15:08:45 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电抗器[JWZN210022JWZN210023]-电气-交接-2021-08-22 | 312 | 电抗器 | 交接 |  | 匡成，文轩 | E8675C23612C905C965FE66F2D015FE8675A3103E1 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-22 00:00:00 | 2021-12-29 16:03:26 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 312 | 电抗器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变1C电容器434串联电抗器A相安装，设备质量无异常 | 归档 | 2021-12-27 16:23:31 | 电容器组串联电抗器 | AC35kV | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 5 | 35kV | 35kV | CKGKL-35-2400/2.88-12% | 天津经纬正能电气设备有限公司 |  | JWZN210022JWZN210023
016010000000000026872740 | 电抗器 | 140300005 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449676 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 17000082 | G1012012 | 500123851 | 6 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 2 | 163158 | 5 | SG2003 | 1 | 已提报 | 电抗器-一般变电站 | 电抗器-一般变电站 | 2021-03-30 15:09:13 | 91AR |  | 1901073598 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电抗器-一般变电站 | 140300005 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"CKGKL-35-2400/2.88-12%","SCCJMC":"天津经纬正能电气设备有限公司","SCCJ":"043352","CCBH":"JWZN210022JWZN210023","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","LQFSMC":"自然空气冷却(AN)","LQFS":"8","DYFSMC":"无调压","DYFS":"3","ZZ":"2.3900","YH":"","YCD":"","QSZ":"","YZ":"","YXJGMC":"","YXJG":"","YZMFFSMC":"","YZMFFS":"","JYNRDJMC":"","JYNRDJ":"","FWDJMC":"","FWDJ":"","EDDY":"35","EDDL":"832.9000","EDPL":"50.0000","JYJZMC":"环氧树脂","JYJZ":"4","DCJGMC":"空芯","DCJG":"1","EDRL":"2400.0000","EDDK":"3.4600","EDDKL":"12.0000","EDDG":"11.0140","EDSH":"27.6000","BFZK":"","EDDSNSDL":"","EDFZNSDL":"","EDDLCXSJ":"","JYSP":"","JYSPZXD":"","LXDK":"","LXYXDGDYBS":"","LXYXDGDLBS":""} | 41311046430000000 | 2021-03-30 15:09:13 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电抗器[JWZN210022JWZN210023]-电气-交接-2021-08-22 | 312 | 电抗器 | 交接 |  | 匡成，文轩 | E8675C23612C905C965FE66F2D015FE8675A3103E1 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-22 00:00:00 | 2021-12-29 16:07:48 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 312 | 电抗器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变1C电容器434串联电抗器B相安装，设备质量无异常 | 归档 | 2021-12-27 16:24:07 | 电容器组串联电抗器 | AC35kV | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 5 | 35kV | 35kV | CKGKL-35-2400/2.88-12% | 天津经纬正能电气设备有限公司 |  | JWZN210022JWZN210023
016010000000000026872757 | 电抗器 | 140300005 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449676 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 17000082 | G1012012 | 500123851 | 6 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 2 | 163158 | 6 | SG2003 | 1 | 已提报 | 电抗器-一般变电站 | 电抗器-一般变电站 | 2021-03-30 15:09:40 | 91AR |  | 1901073598 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电抗器-一般变电站 | 140300005 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"CKGKL-35-2400/2.88-12%","SCCJMC":"天津经纬正能电气设备有限公司","SCCJ":"043352","CCBH":"JWZN210022JWZN210023","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","LQFSMC":"自然空气冷却(AN)","LQFS":"8","DYFSMC":"无调压","DYFS":"3","ZZ":"2.3900","YH":"","YCD":"","QSZ":"","YZ":"","YXJGMC":"","YXJG":"","YZMFFSMC":"","YZMFFS":"","JYNRDJMC":"","JYNRDJ":"","FWDJMC":"","FWDJ":"","EDDY":"35","EDDL":"832.9000","EDPL":"50.0000","JYJZMC":"环氧树脂","JYJZ":"4","DCJGMC":"空芯","DCJG":"1","EDRL":"2400.0000","EDDK":"3.4600","EDDKL":"12.0000","EDDG":"11.0140","EDSH":"27.6000","BFZK":"","EDDSNSDL":"","EDFZNSDL":"","EDDLCXSJ":"","JYSP":"","JYSPZXD":"","LXDK":"","LXYXDGDYBS":"","LXYXDGDLBS":""} | 41311046430000000 | 2021-03-30 15:09:40 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电抗器[JWZN210022JWZN210023]-电气-交接-2021-08-22 | 312 | 电抗器 | 交接 |  | 匡成，文轩 | E8675C23612C905C965FE66F2D015FE8675A3103E1 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-22 00:00:00 | 2021-12-29 16:11:52 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 312 | 电抗器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变1C电容器434串联电抗器C相安装，设备质量无异常 | 归档 | 2021-12-27 16:24:45 | 电容器组串联电抗器 | AC35kV | 电容器组串联电抗器,AC35kV,60000kvar,12%,空心 | 5 | 35kV | 35kV | CKGKL-35-2400/2.88-12% | 天津经纬正能电气设备有限公司 |  | JWZN210022JWZN210023
016010000000000026872764 | 电抗器 | 140300005 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449678 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容器组串联电抗器,AC35kV,60000kvar,5%,空心 | 17000082 | G1012012 | 500125265 | 3 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 3 | 163158 | 1 | SG2003 | 1 | 已提报 | 电抗器-一般变电站 | 电抗器-一般变电站 | 2021-03-30 15:03:38 | 91AR |  | 1901073597 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电抗器-一般变电站 | 140300005 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"CKGKL-35-1000/1.1-5","SCCJMC":"天津经纬正能电气设备有限公司","SCCJ":"043352","CCBH":"JWZN210021","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","LQFSMC":"自然空气冷却(AN)","LQFS":"8","DYFSMC":"无调压","DYFS":"3","ZZ":"1.4000","YH":"","YCD":"","QSZ":"","YZ":"","YXJGMC":"","YXJG":"","YZMFFSMC":"","YZMFFS":"","JYNRDJMC":"","JYNRDJ":"","FWDJMC":"","FWDJ":"","EDDY":"35","EDDL":"909.1000","EDPL":"50.0000","JYJZMC":"环氧树脂","JYJZ":"4","DCJGMC":"空芯","DCJG":"1","EDRL":"1000.0000","EDDK":"1.2100","EDDKL":"5.0000","EDDG":"3.8520","EDSH":"18.4000","BFZK":"","EDDSNSDL":"","EDFZNSDL":"","EDDLCXSJ":"","JYSP":"","JYSPZXD":"","LXDK":"","LXYXDGDYBS":"","LXYXDGDLBS":""} | 41311046430000000 | 2021-03-30 15:03:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电抗器[JWZN210021]-电气-交接-2021-08-22 | 312 | 电抗器 | 交接 |  | 匡成，文轩 | E8675C23612C905C965FE66F2D015FE8675A3103E1 |  |  |  |  | 文轩 |  | 编辑中 |  | 电气试验三队 | 2021-08-22 14:23:28 | 2021-12-29 14:23:28 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 312 | 电抗器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3C电容器446串联电抗器A相安装，设备质量无异常 | 归档 | 2021-12-27 16:46:40 | 电容器组串联电抗器 | AC35kV | 电容器组串联电抗器,AC35kV,60000kvar,5%,空心 | 5 | 35kV | 35kV | CKGKL-35-1000/1.1-5 | 天津经纬正能电气设备有限公司 |  | JWZN210021
016010000000000026872771 | 电抗器 | 140300005 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449678 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容器组串联电抗器,AC35kV,60000kvar,5%,空心 | 17000082 | G1012012 | 500125265 | 3 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 3 | 163158 | 2 | SG2003 | 1 | 已提报 | 电抗器-一般变电站 | 电抗器-一般变电站 | 2021-03-30 15:04:27 | 91AR |  | 1901073597 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电抗器-一般变电站 | 140300005 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"CKGKL-35-1000/1.1-5","SCCJMC":"天津经纬正能电气设备有限公司","SCCJ":"043352","CCBH":"JWZN210021","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","LQFSMC":"自然空气冷却(AN)","LQFS":"8","DYFSMC":"无调压","DYFS":"3","ZZ":"1.4000","YH":"","YCD":"","QSZ":"","YZ":"","YXJGMC":"","YXJG":"","YZMFFSMC":"","YZMFFS":"","JYNRDJMC":"","JYNRDJ":"","FWDJMC":"","FWDJ":"","EDDY":"35","EDDL":"909.1000","EDPL":"50.0000","JYJZMC":"环氧树脂","JYJZ":"4","DCJGMC":"空芯","DCJG":"1","EDRL":"1000.0000","EDDK":"1.2100","EDDKL":"5.0000","EDDG":"3.8520","EDSH":"18.4000","BFZK":"","EDDSNSDL":"","EDFZNSDL":"","EDDLCXSJ":"","JYSP":"","JYSPZXD":"","LXDK":"","LXYXDGDYBS":"","LXYXDGDLBS":""} | 41311046430000000 | 2021-03-30 15:04:27 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电抗器[JWZN210021]-电气-交接-2021-08-22 | 312 | 电抗器 | 交接 |  | 匡成，文轩 | E8675C23612C905C965FE66F2D015FE8675A3103E1 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-22 00:00:00 | 2021-12-29 15:31:18 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 312 | 电抗器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3C电容器446串联电抗器B相安装，设备质量无异常 | 归档 | 2021-12-27 16:47:11 | 电容器组串联电抗器 | AC35kV | 电容器组串联电抗器,AC35kV,60000kvar,5%,空心 | 5 | 35kV | 35kV | CKGKL-35-1000/1.1-5 | 天津经纬正能电气设备有限公司 |  | JWZN210021
016010000000000026872788 | 电抗器 | 140300005 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449678 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容器组串联电抗器,AC35kV,60000kvar,5%,空心 | 17000082 | G1012012 | 500125265 | 3 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000079 | 3 | 163158 | 3 | SG2003 | 1 | 已提报 | 电抗器-一般变电站 | 电抗器-一般变电站 | 2021-03-30 15:04:56 | 91AR |  | 1901073597 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电抗器-一般变电站 | 140300005 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"CKGKL-35-1000/1.1-5","SCCJMC":"天津经纬正能电气设备有限公司","SCCJ":"043352","CCBH":"JWZN210021","CPDH":"","ZZGJMC":"","ZZGJ":"","CCRQ":"20210322","LQFSMC":"自然空气冷却(AN)","LQFS":"8","DYFSMC":"无调压","DYFS":"3","ZZ":"1.4000","YH":"","YCD":"","QSZ":"","YZ":"","YXJGMC":"","YXJG":"","YZMFFSMC":"","YZMFFS":"","JYNRDJMC":"","JYNRDJ":"","FWDJMC":"","FWDJ":"","EDDY":"35","EDDL":"909.1000","EDPL":"50.0000","JYJZMC":"环氧树脂","JYJZ":"4","DCJGMC":"空芯","DCJG":"1","EDRL":"1000.0000","EDDK":"1.2100","EDDKL":"5.0000","EDDG":"3.8520","EDSH":"18.4000","BFZK":"","EDDSNSDL":"","EDFZNSDL":"","EDDLCXSJ":"","JYSP":"","JYSPZXD":"","LXDK":"","LXYXDGDYBS":"","LXYXDGDLBS":""} | 41311046430000000 | 2021-03-30 15:04:56 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电抗器[JWZN210021]-电气-交接-2021-08-22 | 312 | 电抗器 | 交接 |  | 匡成，文轩 | E8675C23612C905C965FE66F2D015FE8675A3103E1 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-22 00:00:00 | 2021-12-29 15:36:42 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 312 | 电抗器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3C电容器446串联电抗器C相安装，设备质量无异常 | 归档 | 2021-12-27 16:47:44 | 电容器组串联电抗器 | AC35kV | 电容器组串联电抗器,AC35kV,60000kvar,5%,空心 | 5 | 35kV | 35kV | CKGKL-35-1000/1.1-5 | 天津经纬正能电气设备有限公司 |  | JWZN210021
016010000000000026872948 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 1 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 09:27:02 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819841','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 09:27:02 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819841]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 17:07:01 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5053电压互感器B相安装，设备质量无异常 | 归档 | 2021-12-27 17:00:04 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026872955 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 2 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 09:46:55 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819842','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 09:46:55 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819842]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 17:18:08 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5053电压互感器C相安装，设备质量无异常 | 归档 | 2021-12-27 17:00:33 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026872962 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 3 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 09:48:28 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819843','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 09:48:28 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819843]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 15:22:41 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5031电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-27 16:56:25 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026872979 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 4 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 09:52:59 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819844','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 09:52:59 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819844]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 15:01:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5013电压互感器B相安装，设备质量无异常 | 归档 | 2021-12-27 16:52:34 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026872986 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 5 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 09:55:11 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819845','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 09:55:11 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819845]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 14:50:10 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5013电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-27 16:52:05 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026872993 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 6 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 09:56:54 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819846','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 09:56:54 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819846]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 15:11:45 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5013电压互感器C相安装，设备质量无异常 | 归档 | 2021-12-27 16:53:08 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873006 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 7 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 10:06:52 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819847','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 10:06:52 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819847]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 |  |  |  |  | 文轩 |  | 编辑中 |  | 电气试验三队 | 2021-08-03 14:32:32 | 2021-12-29 14:32:32 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变500kV母电压互感器A相安装，设备质量无异常安装，设备质量无异常 | 归档 | 2021-12-27 16:48:17 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873013 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 8 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 10:08:21 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819848','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 10:08:21 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819848]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 20:17:19 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变500kV侧5041电压互感器B相安装，设备质量无异常 | 归档 | 2021-12-27 17:02:05 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873020 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 9 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 10:09:54 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819849','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 10:09:54 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819849]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 14:37:06 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变500kV母电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-27 16:48:46 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873037 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 10 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 10:11:30 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819850','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 10:11:30 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819850]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 15:58:34 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5043电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-27 16:57:54 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873044 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 11 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 10:13:13 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819851','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 10:13:13 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819851]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 16:17:28 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5043电压互感器C相安装，设备质量无异常 | 归档 | 2021-12-27 16:58:53 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873051 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 12 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 10:14:47 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819852','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 10:14:47 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819852]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 20:03:50 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变500kV侧5041电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-27 17:01:28 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873068 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 13 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 10:16:17 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819853','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 10:16:17 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819853]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 16:09:15 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5043电压互感器B相安装，设备质量无异常 | 归档 | 2021-12-27 16:58:21 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873075 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 14 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 10:19:11 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819854','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 10:19:11 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819854]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 15:33:28 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5031电压互感器B相安装，设备质量无异常 | 归档 | 2021-12-27 16:56:55 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873082 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 15 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 2 | 163158 | 15 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 10:23:46 | 91AR |  | 1901072857 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819855','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 10:23:46 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819855]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 20:41:44 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变3主变500kV侧5041电压互感器C相，设备质量无异常 | 归档 | 2021-12-27 17:02:43 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873099 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 2 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 1 | 163158 | 1 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 09:13:23 | 91AR |  | 1901072832 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819839','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 09:13:23 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819839]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 15:44:46 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变安南线5031电压互感器C相安装，设备质量无异常 | 归档 | 2021-12-27 16:57:25 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873105 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 17000082 | G1005002 | 500139712 | 2 | 国网湖南电力集中采购工厂 | 日新电机(无锡)有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000089 | 1 | 163158 | 2 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-09-17 09:17:53 | 91AR |  | 1901072832 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'WVB500-5H','SCCJMC':'日新电机（无锡）有限公司','SCCJ':'006114','CCBH':'819840','CPDH':'CVT','ZZGJMC':'中国','ZZGJ':'CN','CCRQ':'20200917','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'单柱式','TXJG':'2','ECXHSCXSMC':'模拟信号','ECXHSCXS':'1','DRQJS':'3','YH':'','SF6QTEDYL':'0.0000','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'无源型','LX':'2','EDDY':'500','EDPL':'50.0000','EDDYB':'(500/√3)/(0.1/√3)/(0.1/√3)/(0.1/√3)/0.1kV','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'31.0000','ZEDDRL':'5000.0000','ECRZSLCL':'2.0000','ECRZSLBH':'2.0000','MFJGMC':'金属膨胀器式','MFJG':'3','JYSP':'840/1865/1350','ZZ':'1350.0000','GD':'6815.0000','EDKLZJDY':'','ZQJCL':'0.2/0.5','ZQJBH':'3P/3P','EDSCRLCL':'10.0000','EDSCRLBH':'30.0000','SJDRL':'15000.0000','ZJDRL':'15000.0000','XJC1DRL':'17260.0000','XJC2DRL':'114500.0000','SCFYB':'','BZ':''} | 41311046430000000 | 2020-09-17 09:17:53 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[819840]-电气-交接-2021-08-03 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-08-03 00:00:00 | 2021-12-30 16:28:52 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变复安线5053电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-27 16:59:31 | 电容式电压互感器 | AC500kV | 电容式电压互感器,AC500kV,油浸/瓷,0.005μF,4,0.5 | 6 | 500kV | [5 empty] | 无效JSON格式
016010000000000026873112 | 开关柜 | 140300034 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449637 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 高压开关柜,AC10kV,过渡柜,小车式,1250A,无开关,无 | 17007766 | G1016001 | 500102890 | 1 | 国网湖南电力集中采购工厂 | 江苏大全长江电器股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000067 | 6 | 163229 | 1 | SG2003 | [5 empty] | 91AR |  | 1901094041 | [32 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 322 | 开关柜 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 314TV柜安装，设备质量无异常 | 归档 | 2021-12-28 10:12:03 | 高压开关柜 | AC10kV | 高压开关柜,AC10kV,过渡柜,小车式,1250A,无开关,无 | 7 | 10kV
016010000000000026873129 | 开关柜 | 140300034 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449635 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 高压开关柜,AC10kV,母线设备柜,小车式,1250A,无开关,无 | 17007766 | G1016001 | 500099478 | 1 | 国网湖南电力集中采购工厂 | 江苏大全长江电器股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000067 | 3 | 163229 | 1 | SG2003 | [5 empty] | 91AR |  | 1901094038 | [32 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 322 | 开关柜 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 302开关柜安装，设备质量无异常 | 归档 | 2021-12-28 10:10:46 | 高压开关柜 | AC10kV | 高压开关柜,AC10kV,母线设备柜,小车式,1250A,无开关,无 | 7 | 10kV
016010000000000026873136 | 开关柜 | 140300034 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449633 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 高压开关柜,AC10kV,站用变开关柜,小车式,1250A,31.5kA,真空 | 17007766 | G1016001 | 500002586 | 1 | 国网湖南电力集中采购工厂 | 江苏大全长江电器股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000067 | 2 | 163229 | 1 | SG2003 | [5 empty] | 91AR |  | 1901094037 | [32 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 322 | 开关柜 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 10kV电缆进线柜安装，设备质量无异常 | 归档 | 2021-12-28 10:11:26 | 高压开关柜 | AC10kV | 高压开关柜,AC10kV,站用变开关柜,小车式,1250A,31.5kA,真空 | 7 | 10kV
016010000000000026872917 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC35kV,油浸/瓷,0.02μF,4,0.5 | 18007253 | G1005002 | 500139717 | 3 | 国网湖南电力集中采购工厂 | 江苏思源赫兹互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000087 | 1 | 163158 | 1 | SG2003 | [5 empty] | 91AR |  | 1901058724 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[]-电气-交接-2021-07-28 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-28 00:00:00 | 2021-12-31 13:51:30 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变35kV母434电压互感器C相安装，设备质量无异常 | 归档 | 2021-12-27 16:21:57 | 电容式电压互感器 | AC35kV | 电容式电压互感器,AC35kV,油浸/瓷,0.02μF,4,0.5 | 6 | 35kV
016010000000000026872924 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC35kV,油浸/瓷,0.02μF,4,0.5 | 18007253 | G1005002 | 500139717 | 3 | 国网湖南电力集中采购工厂 | 江苏思源赫兹互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000087 | 1 | 163158 | 2 | SG2003 | [5 empty] | 91AR |  | 1901058724 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[]-电气-交接-2021-07-28 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-28 00:00:00 | 2021-12-31 13:41:35 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变35kV母434电压互感器B相安装，设备质量无异常 | 归档 | 2021-12-27 16:21:08 | 电容式电压互感器 | AC35kV | 电容式电压互感器,AC35kV,油浸/瓷,0.02μF,4,0.5 | 6 | 35kV
016010000000000026872931 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449653 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC35kV,油浸/瓷,0.02μF,4,0.5 | 18007253 | G1005002 | 500139717 | 3 | 国网湖南电力集中采购工厂 | 江苏思源赫兹互感器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000087 | 1 | 163158 | 3 | SG2003 | [5 empty] | 91AR |  | 1901058724 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[]-电气-交接-2021-07-28 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-28 00:00:00 | 2021-12-31 11:59:08 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 湖南宁乡500千伏变电站新建工程安宁变35kV母434电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-27 16:20:38 | 电容式电压互感器 | AC35kV | 电容式电压互感器,AC35kV,油浸/瓷,0.02μF,4,0.5 | 6 | 35kV
016010000000000026872054 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449661 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 17000160 | G1015002 | 500066608 | 1 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000077 | 2 | 163130 | 1 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-12-09 14:50:59 | 91AR |  | 1901041522 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF11C-252','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201119','LXMC':'GIS','LX':'01','JGXSMC':'断路器分箱、母线共箱','JGXS':'03','EDDY':'252','EDDL':'3150.0000','RWDDL':'50.0000','RWDCXSJ':'3.0000','DLHGQBZFSMC':'外置','DLHGQBZFS':'2','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.4000','SF6QTYLJDBJYLFDLQQS':'0.3500'} | 41311046430000000 | 2020-12-09 14:50:59 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-组合电器[2020]-电气-交接-2021-09-25 | 321 | 组合电器 | 交接 |  | 王策勇，邹晨乔，罗鹏辉，傅刚，何光乐，王涛 | 8B2CDD3D-DAE2-4C44-B430-EC1EF6CA96B6-00008 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 王策勇 | 合格 | 归档 |  | 设备评价所 | 2021-09-25 00:00:00 | 2021-12-25 16:21:01 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变2母联638组合电器安装，设备质量无异常 | 归档 | 2021-12-28 09:33:28 | 220kVHGIS组合电器 | 50kA | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 5 | 50kV | [5 empty] | 无效JSON格式
016010000000000026872061 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449663 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 17000160 | G1015002 | 500066608 | 7 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000077 | 1 | 163130 | 1 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-12-09 14:50:59 | 91AR |  | 1901041521 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF11C-252','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201119','LXMC':'GIS','LX':'01','JGXSMC':'断路器分箱、母线共箱','JGXS':'03','EDDY':'252','EDDL':'3150.0000','RWDDL':'50.0000','RWDCXSJ':'3.0000','DLHGQBZFSMC':'外置','DLHGQBZFS':'2','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.4000','SF6QTYLJDBJYLFDLQQS':'0.3500'} | 41311046430000000 | 2020-12-09 14:50:59 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-组合电器[2020]-电气-交接-2021-09-25 | 321 | 组合电器 | 交接 |  | 邹晨乔，罗鹏辉，傅刚，何光乐，王涛 | 8B2CDD3D-DAE2-4C44-B430-EC1EF6CA96B6-00008 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 邹金星 | 合格 | 归档 |  | 设备评价所 | 2021-09-25 00:00:00 | 2021-12-25 16:33:49 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 调试 | 胡智卿 | 吴浩 | 王坤 | 调试 | 编辑中 | 2021-11-17 11:42:07 | 220kVHGIS组合电器 | 50kA | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 5 | 50kV | [5 empty] | 无效JSON格式
016010000000000026872078 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449663 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 17000160 | G1015002 | 500066608 | 7 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000077 | 1 | 163130 | 2 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-12-09 14:50:59 | 91AR |  | 1901041521 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF11C-252','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201119','LXMC':'GIS','LX':'01','JGXSMC':'断路器分箱、母线共箱','JGXS':'03','EDDY':'252','EDDL':'3150.0000','RWDDL':'50.0000','RWDCXSJ':'3.0000','DLHGQBZFSMC':'外置','DLHGQBZFS':'2','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.4000','SF6QTYLJDBJYLFDLQQS':'0.3500'} | 41311046430000000 | 2020-12-09 14:50:59 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-组合电器[2020]-电气-交接-2021-09-25 | 321 | 组合电器 | 交接 |  | 王策勇，邹晨乔，罗鹏辉，何光乐，王涛，傅刚 | 8B2CDD3D-DAE2-4C44-B430-EC1EF6CA96B6-00008 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 王策勇 | 合格 | 归档 |  | 设备评价所 | 2021-09-25 00:00:00 | 2021-12-25 16:49:03 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变安楚线622组合电器安装，设备质量无异常 | 归档 | 2021-12-28 09:34:42 | 220kVHGIS组合电器 | 50kA | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 5 | 50kV | [5 empty] | 无效JSON格式
016010000000000026872085 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449663 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 17000160 | G1015002 | 500066608 | 7 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000077 | 1 | 163130 | 3 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-12-09 14:50:59 | 91AR |  | 1901041521 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF11C-252','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201119','LXMC':'GIS','LX':'01','JGXSMC':'断路器分箱、母线共箱','JGXS':'03','EDDY':'252','EDDL':'3150.0000','RWDDL':'50.0000','RWDCXSJ':'3.0000','DLHGQBZFSMC':'外置','DLHGQBZFS':'2','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.4000','SF6QTYLJDBJYLFDLQQS':'0.3500'} | 41311046430000000 | 2020-12-09 14:50:59 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-组合电器[2020]-电气-交接-2021-09-25 | 321 | 组合电器 | 交接 |  | 王策勇，邹晨乔，罗鹏辉，何光乐，王涛，傅刚 | 8B2CDD3D-DAE2-4C44-B430-EC1EF6CA96B6-00008 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 王策勇 | 合格 | 归档 |  | 设备评价所 | 2021-09-25 00:00:00 | 2021-12-25 16:54:45 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变安通线634组合电器安装，设备质量无异常 | 归档 | 2021-12-28 09:35:14 | 220kVHGIS组合电器 | 50kA | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 5 | 50kV | [5 empty] | 无效JSON格式
016010000000000026872092 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449663 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 17000160 | G1015002 | 500066608 | 7 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000077 | 1 | 163130 | 4 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-12-09 14:50:59 | 91AR |  | 1901041521 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF11C-252','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201119','LXMC':'GIS','LX':'01','JGXSMC':'断路器分箱、母线共箱','JGXS':'03','EDDY':'252','EDDL':'3150.0000','RWDDL':'50.0000','RWDCXSJ':'3.0000','DLHGQBZFSMC':'外置','DLHGQBZFS':'2','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.4000','SF6QTYLJDBJYLFDLQQS':'0.3500'} | 41311046430000000 | 2020-12-09 14:50:59 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-组合电器[2020]-电气-交接-2021-09-25 | 321 | 组合电器 | 交接 |  | 王策勇，邹晨乔，罗鹏辉，何光乐，王涛，傅刚 | 8B2CDD3D-DAE2-4C44-B430-EC1EF6CA96B6-00008 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 王策勇 | 合格 | 归档 |  | 设备评价所 | 2021-09-25 00:00:00 | 2021-12-25 16:33:49 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变安楚线618组合电器安装，设备质量无异常 | 归档 | 2021-12-28 09:34:08 | 220kVHGIS组合电器 | 50kA | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 5 | 50kV | [5 empty] | 无效JSON格式
016010000000000026872108 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449663 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 17000160 | G1015002 | 500066608 | 7 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000077 | 1 | 163130 | 5 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-12-09 14:50:59 | 91AR |  | 1901041521 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF11C-252','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201119','LXMC':'GIS','LX':'01','JGXSMC':'断路器分箱、母线共箱','JGXS':'03','EDDY':'252','EDDL':'3150.0000','RWDDL':'50.0000','RWDCXSJ':'3.0000','DLHGQBZFSMC':'外置','DLHGQBZFS':'2','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.4000','SF6QTYLJDBJYLFDLQQS':'0.3500'} | 41311046430000000 | 2020-12-09 14:50:59 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-组合电器[2020]-电气-交接-2021-09-25 | 321 | 组合电器 | 交接 |  | 邹晨乔，罗鹏辉，傅刚，何光乐，王涛 | 8B2CDD3D-DAE2-4C44-B430-EC1EF6CA96B6-00008 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 邹金星 | 合格 | 归档 |  | 设备评价所 | 2021-09-25 00:00:00 | 2021-12-25 17:12:27 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变安向线608组合电器安装，设备质量无异常 | 归档 | 2021-12-28 09:35:49 | 220kVHGIS组合电器 | 50kA | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 5 | 50kV | [5 empty] | 无效JSON格式
016010000000000026872115 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449663 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 17000160 | G1015002 | 500066608 | 7 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000077 | 1 | 163130 | 6 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-12-09 14:50:59 | 91AR |  | 1901041521 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF11C-252','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201119','LXMC':'GIS','LX':'01','JGXSMC':'断路器分箱、母线共箱','JGXS':'03','EDDY':'252','EDDL':'3150.0000','RWDDL':'50.0000','RWDCXSJ':'3.0000','DLHGQBZFSMC':'外置','DLHGQBZFS':'2','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.4000','SF6QTYLJDBJYLFDLQQS':'0.3500'} | 41311046430000000 | 2020-12-09 14:50:59 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-组合电器[2020]-电气-交接-2021-09-25 | 321 | 组合电器 | 交接 |  | 邹晨乔，罗鹏辉，傅刚，何光乐，王涛 | 8B2CDD3D-DAE2-4C44-B430-EC1EF6CA96B6-00008 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 邹金星 | 合格 | 归档 |  | 设备评价所 | 2021-09-25 00:00:00 | 2021-12-25 17:04:17 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变安玉线644组合电器安装，设备质量无异常 | 归档 | 2021-12-28 09:36:25 | 220kVHGIS组合电器 | 50kA | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 5 | 50kV | [5 empty] | 无效JSON格式
016010000000000026872122 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449663 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 17000160 | G1015002 | 500066608 | 7 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000077 | 1 | 163130 | 7 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-12-09 14:50:59 | 91AR |  | 1901041521 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF11C-252','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201119','LXMC':'GIS','LX':'01','JGXSMC':'断路器分箱、母线共箱','JGXS':'03','EDDY':'252','EDDL':'3150.0000','RWDDL':'50.0000','RWDCXSJ':'3.0000','DLHGQBZFSMC':'外置','DLHGQBZFS':'2','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.4000','SF6QTYLJDBJYLFDLQQS':'0.3500'} | 41311046430000000 | 2020-12-09 14:50:59 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-组合电器[2020]-电气-交接-2021-09-25 | 321 | 组合电器 | 交接 |  | 邹晨乔，罗鹏辉，傅刚，何光乐，王涛 | 8B2CDD3D-DAE2-4C44-B430-EC1EF6CA96B6-00008 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 邹金星 | 合格 | 归档 |  | 设备评价所 | 2021-09-25 00:00:00 | 2021-12-25 16:52:25 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变安玉线646组合电器安装，设备质量无异常 | 归档 | 2021-12-28 09:36:58 | 220kVHGIS组合电器 | 50kA | 220kVHGIS组合电器,50kA,1CB,4000A,户外 | 5 | 50kV | [5 empty] | 无效JSON格式
016010000000000026872795 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 17000160 | G1005002 | 500139711 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 2 | 163158 | 1 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058462 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-22 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-22 00:00:00 | 2021-12-31 10:47:04 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变安玉线644电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-28 09:40:41 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026872801 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 17000160 | G1005002 | 500139711 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 2 | 163158 | 2 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058462 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-22 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-22 00:00:00 | 2021-12-31 10:29:45 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变安通线634电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-28 09:39:21 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026872818 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 17000160 | G1005002 | 500139711 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 2 | 163158 | 3 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058462 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-22 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-22 00:00:00 | 2021-12-31 10:55:26 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变安玉线646电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-28 09:41:12 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026872825 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 17000160 | G1005002 | 500139711 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 2 | 163158 | 4 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058462 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-22 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 |  |  |  |  | 文轩 |  | 编辑中 |  | 电气试验三队 | 2021-07-22 21:05:12 | 2021-12-30 21:05:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变安楚线618电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-28 09:38:10 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026872832 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 17000160 | G1005002 | 500139711 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 2 | 163158 | 5 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058462 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-22 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-22 00:00:00 | 2021-12-31 10:23:26 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变安楚线622电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-28 09:38:46 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026872849 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449651 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 17000160 | G1005002 | 500139711 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 2 | 163158 | 6 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058462 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-22 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-22 00:00:00 | 2021-12-31 10:38:02 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变安向线608电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-28 09:40:11 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.005μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026872856 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 17000160 | G1005002 | 500139714 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 1 | 163158 | 1 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058463 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-23 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-23 00:00:00 | 2022-01-02 17:20:59 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变614B电压互感器C相安装，设备质量无异常 | 归档 | 2021-12-28 09:42:52 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026872863 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 17000160 | G1005002 | 500139714 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 1 | 163158 | 2 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058463 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-23 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-23 00:00:00 | 2022-01-02 17:27:21 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变624B电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-28 09:43:25 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026872870 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 17000160 | G1005002 | 500139714 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 1 | 163158 | 3 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058463 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-23 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-23 00:00:00 | 2022-01-02 17:40:29 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变624B电压互感器C相安装，设备质量无异常 | 归档 | 2021-12-28 09:44:32 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026872887 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 17000160 | G1005002 | 500139714 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 1 | 163158 | 4 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058463 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-23 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-23 00:00:00 | 2022-01-02 17:34:42 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变624B电压互感器B相安装，设备质量无异常 | 归档 | 2021-12-28 09:43:56 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026872894 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 17000160 | G1005002 | 500139714 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 1 | 163158 | 5 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058463 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-23 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 |  |  |  |  | 文轩 |  | 编辑中 |  | 电气试验三队 | 2021-07-23 14:04:39 | 2021-12-31 14:04:39 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变614B电压互感器A相安装，设备质量无异常 | 归档 | 2021-12-28 09:41:44 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026872900 | 电压互感器 | 140300012 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 17000160 | G1005002 | 500139714 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000088 | 1 | 163158 | 6 | SG2003 | 1 | 已提报 | 电压互感器 | 电压互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901058463 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电压互感器 | 140300012 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'TYD220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'2020','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20201022','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JGXSMC':'电容式','JGXS':'2','TXJGMC':'','TXJG':'','ECXHSCXSMC':'','ECXHSCXS':'','DRQJS':'','YH':'','SF6QTEDYL':'','SF6QTBJYL':'','SJDRQBH':'','SJDRQXS':'','ZJDRQBH':'','ZJDRQXS':'','XJC1DRQBH':'','XJC1DRQXS':'','XJC2DRQBH':'','XJC2DRQXS':'','YCJ':'','YZ':'','SF6QTZL':'','LXMC':'','LX':'','EDDY':'220','EDPL':'50.0000','EDDYB':'0.1/√3：0.1/√3/0.1/√3','CLBB':'','BHBB':'','ECRZZSL':'4.0000','PDBJ':'','ZEDDRL':'','ECRZSLCL':'','ECRZSLBH':'','MFJGMC':'','MFJG':'','JYSP':'','ZZ':'','GD':'','EDKLZJDY':'','ZQJCL':'','ZQJBH':'','EDSCRLCL':'','EDSCRLBH':'','SJDRL':'','ZJDRL':'','XJC1DRL':'','XJC2DRL':'','SCFYB':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电压互感器[2020]-电气-交接-2021-07-23 | 314 | 电压互感器 | 交接 |  | 匡成，文轩 | 608F8EE3052C905CA05E5EFAD5015E608F8A8208C0 | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-07-23 00:00:00 | 2022-01-02 17:11:34 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 314 | 电压互感器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变614B电压互感器B相安装，设备质量无异常 | 归档 | 2021-12-28 09:42:18 | 电容式电压互感器 | AC220kV | 电容式电压互感器,AC220kV,油浸/瓷,0.01μF,4,0.5 | 6 | 220kV | [5 empty] | 无效JSON格式
016010000000000026879923 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605470 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 17000160 | G1003001 | 500137754 | 9 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 2 | 164150 | 1 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121937 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026879930 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605470 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 17000160 | G1003001 | 500137754 | 9 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 2 | 164150 | 2 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121937 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026879947 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605470 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 17000160 | G1003001 | 500137754 | 9 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 2 | 164150 | 3 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121937 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026879954 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605470 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 17000160 | G1003001 | 500137754 | 9 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 2 | 164150 | 4 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121937 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026879961 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605470 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 17000160 | G1003001 | 500137754 | 9 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 2 | 164150 | 5 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121937 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026879978 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605470 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 17000160 | G1003001 | 500137754 | 9 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 2 | 164150 | 6 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121937 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026879985 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605470 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 17000160 | G1003001 | 500137754 | 9 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 2 | 164150 | 7 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121937 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026879992 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605470 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 17000160 | G1003001 | 500137754 | 9 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 2 | 164150 | 8 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121937 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026880004 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605470 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 17000160 | G1003001 | 500137754 | 9 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 2 | 164150 | 9 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121937 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,7,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026880011 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605472 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 17000160 | G1003001 | 500137551 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 1 | 164150 | 1 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121938 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026880028 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605472 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 17000160 | G1003001 | 500137551 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 1 | 164150 | 2 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121938 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026880035 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605472 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 17000160 | G1003001 | 500137551 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 1 | 164150 | 3 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121938 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026880042 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605472 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 17000160 | G1003001 | 500137551 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 1 | 164150 | 4 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121938 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026880059 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605472 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 17000160 | G1003001 | 500137551 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 1 | 164150 | 5 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121938 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026880066 | 电流互感器 | 140300013 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6605472 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 17000160 | G1003001 | 500137551 | 6 | 国网湖南电力集中采购工厂 | 河南平高电气股份有限公司 | X | 主设备 | 1000 | 20200828 | HN20200000605 | 1 | 164150 | 6 | SG2005 | 1 | 已提报 | 电流互感器 | 电流互感器 | 2020-12-09 15:04:12 | 91AR |  | 1901121938 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 电流互感器 | 140300013 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'SWID':'030010000000000001847004','XH':'LVB-220','SCCJMC':'河南平高电气股份有限公司','SCCJ':'003100','CCBH':'','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20190730','JGXSMC':'倒立式','JGXS':'2','JYJZMC':'油浸','JYJZ':'1','WJYXSMC':'瓷质','WJYXS':'1','JYLXMC':'油纸电容型','JYLX':'01','ECXHSCXSMC':'','ECXHSCXS':'','YCCGQYLMC':'','YCCGQYL':'','MFXSMC':'','MFXS':'','YH':'','SF6QTEDYL':'','SF6QTZXYXYL':'','SF6QTBJYL':'','SF6QTZL':'','SF6QTYSYL':'','YZ':'','YCJ':'','GD':'','ZZ':'','CPXH':'','EDDY':'220','EDDL':'2.0000','EDPL':'50.0000','EDDLB':'2*1250/1','CLBB':'','BHBB':'','ECRZZSL':'','JYSP':'','ECRZSLCL':'','ECRZSLBH':'','ECRZSLZTBH':'','ZQJCL':'','ZQJBH':'','ZQJZTBH':'','EDSCRLCL':'','EDSCRLBH':'','EDSCRLZTBH':'','BMJYDYDJ':'','EDYCDL':'','EDKDYCDLXS':'','EDDSRDL':'','EDECSC':'','EDSYSJ':'','FZDY':'','YXBB':'','DWDDL':'125.0000','RWDDL':'50.0000','PDBJ':'','LXRWDDL':'','RWDDLSJ':'','ZDCXDL':'','LDCJDY':'','CZCJDY':'','DSNSDL':'','PDJL':'','ZDCXDY':'','LDCJNYFZ':'','DSRDL':'','CZCJNYFZST':'','ZLNY':'','KSZTDL':'','JBFDSYDY':'','ZLDLCLJD':'','WXDGRSYDY':'','XBDLCLJD':'','JYXY1090':'','BZ':''} | 41311046430000000 | 2020-12-09 15:04:12 | [35 empty] | 500kVSF6电磁CT | 2×2000/1 | 500kVSF6电磁CT,2×2000/1,0.2,TPY,9,15,倒立 | 7 | 2×2000/1 | [5 empty] | 无效JSON格式
016010000000000026872207 | 电抗器 | 140300005 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449674 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV三相油浸一体式并联电抗器,60000kvar,铁芯,不可控,户外 | 17000267 | G1012002 | 500000123 | 2 | 国网湖南电力集中采购工厂 | 特变电工衡阳变压器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000090 | 1 | 163130 | 1 | SG2003 | [5 empty] | 91AR |  | 1901058523 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电抗器[]-化学-交接-2021-08-10 | 312 | 电抗器 | 交接 |  | 赵世华 | DC7EF475822C905C965FDC13F1015FDC7EF31702BA | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 湖南省湘电试验研究院有限公司油化实验室 |  | 王策勇 | 合格 | 审核中 |  | 设备评价所 | 2021-08-10 00:00:00 | 2021-12-27 10:41:13 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 312 | 电抗器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变2L电抗器安装，设备质量无异常 | 归档 | 2021-12-28 09:45:52 | 35kV三相油浸一体式并联电抗器 | 60000kvar | 35kV三相油浸一体式并联电抗器,60000kvar,铁芯,不可控,户外 | 5 | 60000kV
016010000000000026872214 | 电抗器 | 140300005 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449674 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV三相油浸一体式并联电抗器,60000kvar,铁芯,不可控,户外 | 17000267 | G1012002 | 500000123 | 2 | 国网湖南电力集中采购工厂 | 特变电工衡阳变压器有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000090 | 1 | 163130 | 2 | SG2003 | [5 empty] | 91AR |  | 1901058523 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-电抗器[]-化学-交接-2021-08-10 | 312 | 电抗器 | 交接 |  | 赵世华 | DC7EF475822C905C965FDC13F1015FDC7EF31702BA | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 湖南省湘电试验研究院有限公司油化实验室 |  | 王策勇 | 合格 | 审核中 |  | 设备评价所 | 2021-08-10 00:00:00 | 2021-12-27 10:20:56 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 312 | 电抗器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变1L电抗器安装，设备质量无异常 | 归档 | 2021-12-28 09:45:13 | 35kV三相油浸一体式并联电抗器 | 60000kvar | 35kV三相油浸一体式并联电抗器,60000kvar,铁芯,不可控,户外 | 5 | 60000kV
016010000000000026872429 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVHGIS组合电器,63kA,2CB,5000A,户外 | 17002638 | G1015002 | 500074972 | 3 | 国网湖南电力集中采购工厂 | 西安西电开关电气有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000078 | 1 | 163130 | 1 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-09-15 19:42:51 | 91AR |  | 1901054008 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF8A-550','SCCJMC':'西安西电开关电气有限公司','SCCJ':'009367','CCBH':'0000','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20210301','LXMC':'HGIS','LX':'02','JGXSMC':'断路器分箱','JGXS':'04','EDDY':'550','EDDL':'5000.0000','RWDDL':'','RWDCXSJ':'','DLHGQBZFSMC':'','DLHGQBZFS':'','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.5000','SF6QTYLJDBJYLFDLQQS':'0.4500'} | 41311046430000000 | 2020-09-15 19:42:51 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-组合电器[0000]-电气-交接-2021-09-29 | 321 | 组合电器 | 交接 |  | 王策勇，邹晨乔，罗鹏辉，傅刚，何光乐，王涛 | 8B2CDD3D-DAE2-4C44-B430-EC1EF6CA96B6-00008 |  |  |  |  | 吴文兵 |  | 编辑中 |  | 设备评价所 | 2021-09-29 14:37:02 | 2021-12-25 14:37:02 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变安南线5012组合电器安装，设备质量无异常 | 归档 | 2021-12-28 10:05:09 | 500kVHGIS组合电器 | 63kA | 500kVHGIS组合电器,63kA,2CB,5000A,户外 | 5 | 63kV | [5 empty] | 无效JSON格式
016010000000000026872436 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVHGIS组合电器,63kA,2CB,5000A,户外 | 17002638 | G1015002 | 500074972 | 3 | 国网湖南电力集中采购工厂 | 西安西电开关电气有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000078 | 1 | 163130 | 2 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-09-15 19:42:51 | 91AR |  | 1901054008 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF8A-550','SCCJMC':'西安西电开关电气有限公司','SCCJ':'009367','CCBH':'0000','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20180208','LXMC':'HGIS','LX':'02','JGXSMC':'断路器分箱','JGXS':'04','EDDY':'550','EDDL':'5000.0000','RWDDL':'','RWDCXSJ':'','DLHGQBZFSMC':'','DLHGQBZFS':'','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.5000','SF6QTYLJDBJYLFDLQQS':'0.4500'} | 41311046430000000 | 2020-09-15 19:42:51 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 321 | 组合电器 | 交接 |  | 王志强，刘政 | 135E566C-6831-42B2-A712-351E6F9269EC-10697 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 归档 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-31 14:50:20 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变安南线5031组合电器安装，设备质量无异常 | 归档 | 2021-12-28 10:05:49 | 500kVHGIS组合电器 | 63kA | 500kVHGIS组合电器,63kA,2CB,5000A,户外 | 5 | 63kV | [5 empty] | 无效JSON格式
016010000000000026872443 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449649 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVHGIS组合电器,63kA,2CB,5000A,户外 | 17002638 | G1015002 | 500074972 | 3 | 国网湖南电力集中采购工厂 | 西安西电开关电气有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000078 | 1 | 163130 | 3 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-09-15 19:42:51 | 91AR |  | 1901054008 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF8A-550','SCCJMC':'西安西电开关电气有限公司','SCCJ':'009367','CCBH':'0000','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20210301','LXMC':'HGIS','LX':'02','JGXSMC':'断路器分箱','JGXS':'04','EDDY':'550','EDDL':'5000.0000','RWDDL':'','RWDCXSJ':'','DLHGQBZFSMC':'','DLHGQBZFS':'','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.5000','SF6QTYLJDBJYLFDLQQS':'0.4500'} | 41311046430000000 | 2020-09-15 19:42:51 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-组合电器[0000]-电气-交接-2021-09-29 | 321 | 组合电器 | 交接 |  | 邹晨乔，向缨竹，罗鹏辉，傅刚，何光乐，王涛 | 8B2CDD3D-DAE2-4C44-B430-EC1EF6CA96B6-00008 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 邹金星 | 合格 | 归档 |  | 设备评价所 | 2021-09-29 00:00:00 | 2021-12-25 17:30:16 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变复安线5053组合电器安装，设备质量无异常 | 归档 | 2021-12-28 10:07:02 | 500kVHGIS组合电器 | 63kA | 500kVHGIS组合电器,63kA,2CB,5000A,户外 | 5 | 63kV | [5 empty] | 无效JSON格式
016010000000000026872450 | 组合电器 | 140300028 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449647 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 500kVHGIS组合电器,63kA,3CB,5000A,户外 | 17002638 | G1015002 | 500056361 | 1 | 国网湖南电力集中采购工厂 | 西安西电开关电气有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000078 | 2 | 163130 | 1 | SG2003 | 1 | 已提报 | 组合电器 | 组合电器 | 2020-09-15 19:42:51 | 91AR |  | 1901054009 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 组合电器 | 140300028 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {'XH':'ZF8A-550','SCCJMC':'西安西电开关电气有限公司','SCCJ':'009367','CCBH':'0000','CPDH':'','ZZGJMC':'','ZZGJ':'','CCRQ':'20210301','LXMC':'HGIS','LX':'02','JGXSMC':'断路器分箱、母线分箱','JGXS':'02','EDDY':'550','EDDL':'5000.0000','RWDDL':'','RWDCXSJ':'','DLHGQBZFSMC':'','DLHGQBZFS':'','JCXFSMC':'架空','JCXFS':'1','SF6QTEDYLFDLQQS':'0.5000','SF6QTYLJDBJYLFDLQQS':'0.4500'} | 41311046430000000 | 2020-09-15 19:42:51 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-组合电器[0000]-电气-交接-2021-09-29 | 321 | 组合电器 | 交接 |  | 王策勇,向缨竹,邹晨乔,罗鹏辉,何光乐,王涛,傅刚 | 8B2CDD3D-DAE2-4C44-B430-EC1EF6CA96B6-00008 | 国网湖南省电力有限公司 | 湖南省湘电试验研究院有限公司 | 500kV安宁变电站 |  | 王策勇 | 合格 | 归档 |  | 设备评价所 | 2021-09-29 00:00:00 | 2021-12-25 17:12:45 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 321 | 组合电器 | 安装 | 李立 | 李鸽、李浩洋、曾海波等 | 金吉发 | 安宁变3主变500kV侧5041组合电器安装，设备质量无异常 | 归档 | 2021-12-28 10:06:30 | 500kVHGIS组合电器 | 63kA | 500kVHGIS组合电器,63kA,3CB,5000A,户外 | 5 | 63kV | [5 empty] | 无效JSON格式
016010000000000025789636 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449661 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 17002490 | G1010001 | 500002322 | 7 | 国网湖南电力集中采购工厂 | 西安西电高压开关有限责任公司 | X | 主设备 | 1000 | 20200630 | HN20200000069 | 1 | 172936 | 1 | SG2003 | [5 empty] | 91AR |  | 1901097547 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[]-电气-交接-2021-10-04 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 编辑中 |  | 电气试验三队 | 2021-10-04 00:00:00 | 2021-12-31 14:51:56 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变2C电容器4381隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:58:33 | 35kV三相隔离开关 | 2500A | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 5 | 2500A
016010000000000025789643 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449661 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 17002490 | G1010001 | 500002322 | 7 | 国网湖南电力集中采购工厂 | 西安西电高压开关有限责任公司 | X | 主设备 | 1000 | 20200630 | HN20200000069 | 1 | 172936 | 2 | SG2003 | [5 empty] | 91AR |  | 1901097547 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[]-电气-交接-2021-10-04 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 编辑中 |  | 电气试验三队 | 2021-10-04 00:00:00 | 2021-12-31 14:43:04 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变1C电容器4341隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:57:12 | 35kV三相隔离开关 | 2500A | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 5 | 2500A
016010000000000025789650 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449661 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 17002490 | G1010001 | 500002322 | 7 | 国网湖南电力集中采购工厂 | 西安西电高压开关有限责任公司 | X | 主设备 | 1000 | 20200630 | HN20200000069 | 1 | 172936 | 3 | SG2003 | [5 empty] | 91AR |  | 1901097547 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[]-电气-交接-2021-10-04 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 编辑中 |  | 电气试验三队 | 2021-10-04 00:00:00 | 2021-12-31 15:08:47 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变直流融冰4441隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 10:00:21 | 35kV三相隔离开关 | 2500A | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 5 | 2500A
016010000000000025789667 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449661 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 17002490 | G1010001 | 500002322 | 7 | 国网湖南电力集中采购工厂 | 西安西电高压开关有限责任公司 | X | 主设备 | 1000 | 20200630 | HN20200000069 | 1 | 172936 | 4 | SG2003 | [5 empty] | 91AR |  | 1901097547 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[]-电气-交接-2021-02-14 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 编辑中 |  | 电气试验三队 | 2021-02-14 00:00:00 | 2021-12-31 15:04:54 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变3C电容器4461隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:59:49 | 35kV三相隔离开关 | 2500A | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 5 | 2500A
016010000000000025789674 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449661 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 17002490 | G1010001 | 500002322 | 7 | 国网湖南电力集中采购工厂 | 西安西电高压开关有限责任公司 | X | 主设备 | 1000 | 20200630 | HN20200000069 | 1 | 172936 | 5 | SG2003 | [5 empty] | 91AR |  | 1901097547 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[]-电气-交接-2021-10-04 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 编辑中 |  | 电气试验三队 | 2021-10-04 00:00:00 | 2021-12-31 14:32:57 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变2站用变4321隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:56:39 | 35kV三相隔离开关 | 2500A | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 5 | 2500A
016010000000000025789681 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449661 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 17002490 | G1010001 | 500002322 | 7 | 国网湖南电力集中采购工厂 | 西安西电高压开关有限责任公司 | X | 主设备 | 1000 | 20200630 | HN20200000069 | 1 | 172936 | 6 | SG2003 | [5 empty] | 91AR |  | 1901097547 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[]-电气-交接-2021-10-04 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 编辑中 |  | 电气试验三队 | 2021-10-04 00:00:00 | 2021-12-31 14:48:38 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变1L电抗器4361隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:57:47 | 35kV三相隔离开关 | 2500A | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 5 | 2500A
016010000000000025789698 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449661 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 17002490 | G1010001 | 500002322 | 7 | 国网湖南电力集中采购工厂 | 西安西电高压开关有限责任公司 | X | 主设备 | 1000 | 20200630 | HN20200000069 | 1 | 172936 | 7 | SG2003 | [5 empty] | 91AR |  | 1901097547 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[]-电气-交接-2021-10-04 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 编辑中 |  | 电气试验三队 | 2021-10-04 00:00:00 | 2021-12-31 15:01:21 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变2L电抗器4421隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:59:04 | 35kV三相隔离开关 | 2500A | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,单接地 | 5 | 2500A
016010000000000025789704 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449659 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV三相隔离开关,4000A,40kA,电动双柱水平旋转,双接地 | 17002490 | G1010001 | 500002335 | 1 | 国网湖南电力集中采购工厂 | 西安西电高压开关有限责任公司 | X | 主设备 | 1000 | 20200630 | HN20200000069 | 2 | 172936 | 1 | SG2003 | [5 empty] | 91AR |  | 1901097548 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[]-电气-交接-2021-10-04 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D |  |  |  |  | 文轩 |  | 编辑中 |  | 电气试验三队 | 2021-10-04 16:50:17 | 2022-01-04 16:50:17 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变3主变4303隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 10:01:26 | 35kV三相隔离开关 | 4000A | 35kV三相隔离开关,4000A,40kA,电动双柱水平旋转,双接地 | 5 | 4000A
016010000000000025789711 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449663 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,双接地 | 17002490 | G1010001 | 500002323 | 1 | 国网湖南电力集中采购工厂 | 西安西电高压开关有限责任公司 | X | 主设备 | 1000 | 20200630 | HN20200000069 | 3 | 172936 | 1 | SG2003 | [5 empty] | 91AR |  | 1901097549 | [10 empty] | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[]-电气-交接-2021-10-04 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D |  |  |  |  | 文轩 |  | 编辑中 |  | 电气试验三队 | 2021-10-04 15:11:53 | 2021-12-31 15:11:53 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变434隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 10:00:53 | 35kV三相隔离开关 | 2500A | 35kV三相隔离开关,2500A,40kA,电动双柱水平旋转,双接地 | 5 | 2500A
016010000000000026872498 | 断路器 | 140300001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 17000119 | G1008001 | 500003723 | 8 | 国网湖南电力集中采购工厂 | 西门子(杭州)高压开关有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000073 | 1 | 163130 | 1 | SG2003 | 1 | 已提报 | 断路器 | 断路器 | 2021-03-26 14:54:23 | 91AR |  | 1901055752 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 断路器 | 140300001 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"3AP1-FG","SCCJMC":"西门子（杭州）高压开关有限公司","SCCJ":"009437","CCBH":"20/K40044598","CCRQ":"20210430","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","YCJ":"","CNDJXH":"","EDDY":"72.5kV","EDDL":"4000.0000","EDPL":"50.0000","JGXSMC":"瓷柱式","JGXS":"01","CZJGXSMC":"弹簧","CZJGXS":"01","MHJZMC":"SF6","MHJZ":"01","EDGZYL":"0.6000","EDJYSP":"140kV","EDDLKDDL":"40.0000","EDDLDLKDCS":"40.0000","EDDLGHDL":"100.0000","EDFZNSDL":"100.0000","EDDSNSDL":"40.0000","EDDSCXSJ":"3.0000","DKSL":"1.0000","TGPDJL":"","TGGHJL":"","DDXLBJ":"","JXSM":"10000.0000","SF6QTEDYL":"0.6000","SF6QTBJYL":"0.5200","SF6QTBSYL":"0.5000","HZBSCZYL":"","FZBSCZYL":"","ZHZBSYL":"","ZDYXTZCS":"","EDSBKDDL":"","JQGZKDDL":"","EDXLCDKDDL":"","EDDLCDKDDL":"","EDLDCJNSDYDD":"","EDLDCJNSDYXJ":"","EDLDCJNSDYDK":"","YFZGPNYDD":"","YFZGPNYXJ":"","YFZGPNYDK":"","FZHLEDDYDY":"","DKXLBJ":"","CZJGEDCZDY":"","YZDX":"","YH":"","SF6QTZL":"","CNDJDY":"","CNSJ":"","QDYL":"","TZYL":"","HZJCBSCZYL":"","FZJCBSCZYL":"","ZHZBSJCCZYL":"","YCSGYL":"","YCJDYL":"","AQFDZYL":"","AQFDZFHYL":"","HZDZ":"","HZSJ":"55±8","FZSJ":"23±2","HFSJJSDJSJ":"30±10","SXFZBTQ":"","SXHZBTQ":"","TXFZBTQ":"","TXHZBTQ":"","RWDDL":"40.0000","DWDDL":"100.0000"} | 41311046430000000 | 2021-03-26 14:54:23 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 305 | 断路器 | 交接 |  | 王志强，刘政 | D134260A-551B-451D-91C4-FBD63B1348EE-00010 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 归档 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-28 10:41:15 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 305 | 断路器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变1L电抗器436断路器安装，设备质量无异常 | 归档 | 2021-12-28 09:28:29 | 66kVSF6瓷柱式断路器 | 4000A | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 5 | 4000A | 72.5kVkV | 3AP1-FG | 西门子（杭州）高压开关有限公司 | 瓷柱式 | 20/K40044598
016010000000000026872504 | 断路器 | 140300001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 17000119 | G1008001 | 500003723 | 8 | 国网湖南电力集中采购工厂 | 西门子(杭州)高压开关有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000073 | 1 | 163130 | 2 | SG2003 | 1 | 已提报 | 断路器 | 断路器 | 2021-03-26 14:54:23 | 91AR |  | 1901055752 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 断路器 | 140300001 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"3AP1-FG","SCCJMC":"西门子（杭州）高压开关有限公司","SCCJ":"009437","CCBH":"20/K40044597","CCRQ":"20210430","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","YCJ":"","CNDJXH":"","EDDY":"72.5kV","EDDL":"4000.0000","EDPL":"50.0000","JGXSMC":"瓷柱式","JGXS":"01","CZJGXSMC":"弹簧","CZJGXS":"01","MHJZMC":"SF6","MHJZ":"01","EDGZYL":"0.6000","EDJYSP":"140kV","EDDLKDDL":"40.0000","EDDLDLKDCS":"40.0000","EDDLGHDL":"100.0000","EDFZNSDL":"100.0000","EDDSNSDL":"40.0000","EDDSCXSJ":"3.0000","DKSL":"1.0000","TGPDJL":"","TGGHJL":"","DDXLBJ":"","JXSM":"10000.0000","SF6QTEDYL":"0.6000","SF6QTBJYL":"0.5200","SF6QTBSYL":"0.5000","HZBSCZYL":"","FZBSCZYL":"","ZHZBSYL":"","ZDYXTZCS":"","EDSBKDDL":"","JQGZKDDL":"","EDXLCDKDDL":"","EDDLCDKDDL":"","EDLDCJNSDYDD":"","EDLDCJNSDYXJ":"","EDLDCJNSDYDK":"","YFZGPNYDD":"","YFZGPNYXJ":"","YFZGPNYDK":"","FZHLEDDYDY":"","DKXLBJ":"","CZJGEDCZDY":"","YZDX":"","YH":"","SF6QTZL":"","CNDJDY":"","CNSJ":"","QDYL":"","TZYL":"","HZJCBSCZYL":"","FZJCBSCZYL":"","ZHZBSJCCZYL":"","YCSGYL":"","YCJDYL":"","AQFDZYL":"","AQFDZFHYL":"","HZDZ":"","HZSJ":"55±8","FZSJ":"23±2","HFSJJSDJSJ":"30±10","SXFZBTQ":"","SXHZBTQ":"","TXFZBTQ":"","TXHZBTQ":"","RWDDL":"40.0000","DWDDL":"100.0000"} | 41311046430000000 | 2021-03-26 14:54:23 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 305 | 断路器 | 交接 |  | 王志强，刘政 | D134260A-551B-451D-91C4-FBD63B1348EE-00010 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 归档 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-28 10:52:14 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 305 | 断路器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变直流融冰444断路器安装，设备质量无异常 | 归档 | 2021-12-28 09:31:22 | 66kVSF6瓷柱式断路器 | 4000A | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 5 | 4000A | 72.5kVkV | 3AP1-FG | 西门子（杭州）高压开关有限公司 | 瓷柱式 | 20/K40044597
016010000000000026872511 | 断路器 | 140300001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 17000119 | G1008001 | 500003723 | 8 | 国网湖南电力集中采购工厂 | 西门子(杭州)高压开关有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000073 | 1 | 163130 | 3 | SG2003 | 1 | 已提报 | 断路器 | 断路器 | 2021-03-26 14:54:23 | 91AR |  | 1901055752 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 断路器 | 140300001 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"3AP1-FG","SCCJMC":"西门子（杭州）高压开关有限公司","SCCJ":"009437","CCBH":"20/K40044596","CCRQ":"20210430","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","YCJ":"","CNDJXH":"","EDDY":"72.5kV","EDDL":"4000.0000","EDPL":"50.0000","JGXSMC":"瓷柱式","JGXS":"01","CZJGXSMC":"弹簧","CZJGXS":"01","MHJZMC":"SF6","MHJZ":"01","EDGZYL":"0.6000","EDJYSP":"140kV","EDDLKDDL":"40.0000","EDDLDLKDCS":"40.0000","EDDLGHDL":"100.0000","EDFZNSDL":"100.0000","EDDSNSDL":"40.0000","EDDSCXSJ":"3.0000","DKSL":"1.0000","TGPDJL":"","TGGHJL":"","DDXLBJ":"","JXSM":"10000.0000","SF6QTEDYL":"0.6000","SF6QTBJYL":"0.5200","SF6QTBSYL":"0.5000","HZBSCZYL":"","FZBSCZYL":"","ZHZBSYL":"","ZDYXTZCS":"","EDSBKDDL":"","JQGZKDDL":"","EDXLCDKDDL":"","EDDLCDKDDL":"","EDLDCJNSDYDD":"","EDLDCJNSDYXJ":"","EDLDCJNSDYDK":"","YFZGPNYDD":"","YFZGPNYXJ":"","YFZGPNYDK":"","FZHLEDDYDY":"","DKXLBJ":"","CZJGEDCZDY":"","YZDX":"","YH":"","SF6QTZL":"","CNDJDY":"","CNSJ":"","QDYL":"","TZYL":"","HZJCBSCZYL":"","FZJCBSCZYL":"","ZHZBSJCCZYL":"","YCSGYL":"","YCJDYL":"","AQFDZYL":"","AQFDZFHYL":"","HZDZ":"","HZSJ":"55±8","FZSJ":"23±2","HFSJJSDJSJ":"30±10","SXFZBTQ":"","SXHZBTQ":"","TXFZBTQ":"","TXHZBTQ":"","RWDDL":"40.0000","DWDDL":"100.0000"} | 41311046430000000 | 2021-03-26 14:54:23 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 305 | 断路器 | 交接 |  | 王志强，刘政 | D134260A-551B-451D-91C4-FBD63B1348EE-00010 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 归档 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-28 10:44:52 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 305 | 断路器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变2C电容器438断路器安装，设备质量无异常 | 归档 | 2021-12-28 09:29:05 | 66kVSF6瓷柱式断路器 | 4000A | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 5 | 4000A | 72.5kVkV | 3AP1-FG | 西门子（杭州）高压开关有限公司 | 瓷柱式 | 20/K40044596
016010000000000026872528 | 断路器 | 140300001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 17000119 | G1008001 | 500003723 | 8 | 国网湖南电力集中采购工厂 | 西门子(杭州)高压开关有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000073 | 1 | 163130 | 4 | SG2003 | 1 | 已提报 | 断路器 | 断路器 | 2021-03-26 14:54:23 | 91AR |  | 1901055752 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 断路器 | 140300001 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"3AP1-FG","SCCJMC":"西门子（杭州）高压开关有限公司","SCCJ":"009437","CCBH":"20/K40044595","CCRQ":"20210430","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","YCJ":"","CNDJXH":"","EDDY":"72.5kV","EDDL":"4000.0000","EDPL":"50.0000","JGXSMC":"瓷柱式","JGXS":"01","CZJGXSMC":"弹簧","CZJGXS":"01","MHJZMC":"SF6","MHJZ":"01","EDGZYL":"0.6000","EDJYSP":"140kV","EDDLKDDL":"40.0000","EDDLDLKDCS":"40.0000","EDDLGHDL":"100.0000","EDFZNSDL":"100.0000","EDDSNSDL":"40.0000","EDDSCXSJ":"3.0000","DKSL":"1.0000","TGPDJL":"","TGGHJL":"","DDXLBJ":"","JXSM":"10000.0000","SF6QTEDYL":"0.6000","SF6QTBJYL":"0.5200","SF6QTBSYL":"0.5000","HZBSCZYL":"","FZBSCZYL":"","ZHZBSYL":"","ZDYXTZCS":"","EDSBKDDL":"","JQGZKDDL":"","EDXLCDKDDL":"","EDDLCDKDDL":"","EDLDCJNSDYDD":"","EDLDCJNSDYXJ":"","EDLDCJNSDYDK":"","YFZGPNYDD":"","YFZGPNYXJ":"","YFZGPNYDK":"","FZHLEDDYDY":"","DKXLBJ":"","CZJGEDCZDY":"","YZDX":"","YH":"","SF6QTZL":"","CNDJDY":"","CNSJ":"","QDYL":"","TZYL":"","HZJCBSCZYL":"","FZJCBSCZYL":"","ZHZBSJCCZYL":"","YCSGYL":"","YCJDYL":"","AQFDZYL":"","AQFDZFHYL":"","HZDZ":"","HZSJ":"55±8","FZSJ":"23±2","HFSJJSDJSJ":"30±10","SXFZBTQ":"","SXHZBTQ":"","TXFZBTQ":"","TXHZBTQ":"","RWDDL":"40.0000","DWDDL":"100.0000"} | 41311046430000000 | 2021-03-26 14:54:23 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 305 | 断路器 | 交接 |  | 王志强，刘政 | D134260A-551B-451D-91C4-FBD63B1348EE-00010 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 归档 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-28 10:49:41 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 305 | 断路器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变3C电容器446断路器安装，设备质量无异常 | 归档 | 2021-12-28 09:30:46 | 66kVSF6瓷柱式断路器 | 4000A | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 5 | 4000A | 72.5kVkV | 3AP1-FG | 西门子（杭州）高压开关有限公司 | 瓷柱式 | 20/K40044595
016010000000000026872535 | 断路器 | 140300001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 17000119 | G1008001 | 500003723 | 8 | 国网湖南电力集中采购工厂 | 西门子(杭州)高压开关有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000073 | 1 | 163130 | 5 | SG2003 | 1 | 已提报 | 断路器 | 断路器 | 2021-03-26 14:54:23 | 91AR |  | 1901055752 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 断路器 | 140300001 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"3AP1-FG","SCCJMC":"西门子（杭州）高压开关有限公司","SCCJ":"009437","CCBH":"20/K40044594","CCRQ":"20210430","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","YCJ":"","CNDJXH":"","EDDY":"72.5kV","EDDL":"4000.0000","EDPL":"50.0000","JGXSMC":"瓷柱式","JGXS":"01","CZJGXSMC":"弹簧","CZJGXS":"01","MHJZMC":"SF6","MHJZ":"01","EDGZYL":"0.6000","EDJYSP":"140kV","EDDLKDDL":"40.0000","EDDLDLKDCS":"40.0000","EDDLGHDL":"100.0000","EDFZNSDL":"100.0000","EDDSNSDL":"40.0000","EDDSCXSJ":"3.0000","DKSL":"1.0000","TGPDJL":"","TGGHJL":"","DDXLBJ":"","JXSM":"10000.0000","SF6QTEDYL":"0.6000","SF6QTBJYL":"0.5200","SF6QTBSYL":"0.5000","HZBSCZYL":"","FZBSCZYL":"","ZHZBSYL":"","ZDYXTZCS":"","EDSBKDDL":"","JQGZKDDL":"","EDXLCDKDDL":"","EDDLCDKDDL":"","EDLDCJNSDYDD":"","EDLDCJNSDYXJ":"","EDLDCJNSDYDK":"","YFZGPNYDD":"","YFZGPNYXJ":"","YFZGPNYDK":"","FZHLEDDYDY":"","DKXLBJ":"","CZJGEDCZDY":"","YZDX":"","YH":"","SF6QTZL":"","CNDJDY":"","CNSJ":"","QDYL":"","TZYL":"","HZJCBSCZYL":"","FZJCBSCZYL":"","ZHZBSJCCZYL":"","YCSGYL":"","YCJDYL":"","AQFDZYL":"","AQFDZFHYL":"","HZDZ":"","HZSJ":"55±8","FZSJ":"23±2","HFSJJSDJSJ":"30±10","SXFZBTQ":"","SXHZBTQ":"","TXFZBTQ":"","TXHZBTQ":"","RWDDL":"40.0000","DWDDL":"100.0000"} | 41311046430000000 | 2021-03-26 14:54:23 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 305 | 断路器 | 交接 |  | 王志强，刘政 | D134260A-551B-451D-91C4-FBD63B1348EE-00010 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 归档 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-28 10:54:41 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 305 | 断路器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变3主变430断路器安装，设备质量无异常 | 归档 | 2021-12-28 09:31:56 | 66kVSF6瓷柱式断路器 | 4000A | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 5 | 4000A | 72.5kVkV | 3AP1-FG | 西门子（杭州）高压开关有限公司 | 瓷柱式 | 20/K40044594
016010000000000026872542 | 断路器 | 140300001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 17000119 | G1008001 | 500003723 | 8 | 国网湖南电力集中采购工厂 | 西门子(杭州)高压开关有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000073 | 1 | 163130 | 6 | SG2003 | 1 | 已提报 | 断路器 | 断路器 | 2021-03-26 14:54:23 | 91AR |  | 1901055752 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 断路器 | 140300001 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"3AP1-FG","SCCJMC":"西门子（杭州）高压开关有限公司","SCCJ":"009437","CCBH":"20/K400445913","CCRQ":"20210430","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","YCJ":"","CNDJXH":"","EDDY":"72.5kV","EDDL":"4000.0000","EDPL":"50.0000","JGXSMC":"瓷柱式","JGXS":"01","CZJGXSMC":"弹簧","CZJGXS":"01","MHJZMC":"SF6","MHJZ":"01","EDGZYL":"0.6000","EDJYSP":"140kV","EDDLKDDL":"40.0000","EDDLDLKDCS":"40.0000","EDDLGHDL":"100.0000","EDFZNSDL":"100.0000","EDDSNSDL":"40.0000","EDDSCXSJ":"3.0000","DKSL":"1.0000","TGPDJL":"","TGGHJL":"","DDXLBJ":"","JXSM":"10000.0000","SF6QTEDYL":"0.6000","SF6QTBJYL":"0.5200","SF6QTBSYL":"0.5000","HZBSCZYL":"","FZBSCZYL":"","ZHZBSYL":"","ZDYXTZCS":"","EDSBKDDL":"","JQGZKDDL":"","EDXLCDKDDL":"","EDDLCDKDDL":"","EDLDCJNSDYDD":"","EDLDCJNSDYXJ":"","EDLDCJNSDYDK":"","YFZGPNYDD":"","YFZGPNYXJ":"","YFZGPNYDK":"","FZHLEDDYDY":"","DKXLBJ":"","CZJGEDCZDY":"","YZDX":"","YH":"","SF6QTZL":"","CNDJDY":"","CNSJ":"","QDYL":"","TZYL":"","HZJCBSCZYL":"","FZJCBSCZYL":"","ZHZBSJCCZYL":"","YCSGYL":"","YCJDYL":"","AQFDZYL":"","AQFDZFHYL":"","HZDZ":"","HZSJ":"55±8","FZSJ":"23±2","HFSJJSDJSJ":"30±10","SXFZBTQ":"","SXHZBTQ":"","TXFZBTQ":"","TXHZBTQ":"","RWDDL":"40.0000","DWDDL":"100.0000"} | 41311046430000000 | 2021-03-26 14:54:23 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-断路器[20/K400445913]-电气-交接-2021-12-01 | 305 | 断路器 | 交接 |  | 匡成，文轩 | 50065FA6F32C905CA05E4F9396015E50065E80024A |  |  |  |  | 文轩 |  | 编辑中 |  | 电气试验三队 | 2021-12-01 19:27:29 | 2021-12-27 19:27:29 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 305 | 断路器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变2站用变432断路器安装，设备质量无异常 | 归档 | 2021-12-28 09:22:22 | 66kVSF6瓷柱式断路器 | 4000A | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 5 | 4000A | 72.5kVkV | 3AP1-FG | 西门子（杭州）高压开关有限公司 | 瓷柱式 | 20/K400445913
016010000000000026872559 | 断路器 | 140300001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 17000119 | G1008001 | 500003723 | 8 | 国网湖南电力集中采购工厂 | 西门子(杭州)高压开关有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000073 | 1 | 163130 | 7 | SG2003 | 1 | 已提报 | 断路器 | 断路器 | 2021-03-26 14:54:23 | 91AR |  | 1901055752 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 断路器 | 140300001 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"3AP1-FG","SCCJMC":"西门子（杭州）高压开关有限公司","SCCJ":"009437","CCBH":"20/K40044592","CCRQ":"20210430","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","YCJ":"","CNDJXH":"","EDDY":"72.5kV","EDDL":"4000.0000","EDPL":"50.0000","JGXSMC":"瓷柱式","JGXS":"01","CZJGXSMC":"弹簧","CZJGXS":"01","MHJZMC":"SF6","MHJZ":"01","EDGZYL":"0.6000","EDJYSP":"140kV","EDDLKDDL":"40.0000","EDDLDLKDCS":"40.0000","EDDLGHDL":"100.0000","EDFZNSDL":"100.0000","EDDSNSDL":"40.0000","EDDSCXSJ":"3.0000","DKSL":"1.0000","TGPDJL":"","TGGHJL":"","DDXLBJ":"","JXSM":"10000.0000","SF6QTEDYL":"0.6000","SF6QTBJYL":"0.5200","SF6QTBSYL":"0.5000","HZBSCZYL":"","FZBSCZYL":"","ZHZBSYL":"","ZDYXTZCS":"","EDSBKDDL":"","JQGZKDDL":"","EDXLCDKDDL":"","EDDLCDKDDL":"","EDLDCJNSDYDD":"","EDLDCJNSDYXJ":"","EDLDCJNSDYDK":"","YFZGPNYDD":"","YFZGPNYXJ":"","YFZGPNYDK":"","FZHLEDDYDY":"","DKXLBJ":"","CZJGEDCZDY":"","YZDX":"","YH":"","SF6QTZL":"","CNDJDY":"","CNSJ":"","QDYL":"","TZYL":"","HZJCBSCZYL":"","FZJCBSCZYL":"","ZHZBSJCCZYL":"","YCSGYL":"","YCJDYL":"","AQFDZYL":"","AQFDZFHYL":"","HZDZ":"","HZSJ":"55±8","FZSJ":"23±2","HFSJJSDJSJ":"30±10","SXFZBTQ":"","SXHZBTQ":"","TXFZBTQ":"","TXHZBTQ":"","RWDDL":"40.0000","DWDDL":"100.0000"} | 41311046430000000 | 2021-03-26 14:54:23 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 305 | 断路器 | 交接 |  | 王志强，刘政 | D134260A-551B-451D-91C4-FBD63B1348EE-00010 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 归档 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-28 10:38:44 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 305 | 断路器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变1C电容器434断路器安装，设备质量无异常 | 归档 | 2021-12-28 09:27:45 | 66kVSF6瓷柱式断路器 | 4000A | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 5 | 4000A | 72.5kVkV | 3AP1-FG | 西门子（杭州）高压开关有限公司 | 瓷柱式 | 20/K40044592
016010000000000026872566 | 断路器 | 140300001 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449657 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 17000119 | G1008001 | 500003723 | 8 | 国网湖南电力集中采购工厂 | 西门子(杭州)高压开关有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000073 | 1 | 163130 | 8 | SG2003 | 1 | 已提报 | 断路器 | 断路器 | 2021-03-26 14:54:23 | 91AR |  | 1901055752 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 断路器 | 140300001 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"3AP1-FG","SCCJMC":"西门子（杭州）高压开关有限公司","SCCJ":"009437","CCBH":"20/K40044591","CCRQ":"20210430","CPDH":"","ZZGJMC":"中国","ZZGJ":"CN","YCJ":"","CNDJXH":"","EDDY":"72.5kV","EDDL":"4000.0000","EDPL":"50.0000","JGXSMC":"瓷柱式","JGXS":"01","CZJGXSMC":"弹簧","CZJGXS":"01","MHJZMC":"SF6","MHJZ":"01","EDGZYL":"0.6000","EDJYSP":"140kV","EDDLKDDL":"40.0000","EDDLDLKDCS":"40.0000","EDDLGHDL":"100.0000","EDFZNSDL":"100.0000","EDDSNSDL":"40.0000","EDDSCXSJ":"3.0000","DKSL":"1.0000","TGPDJL":"","TGGHJL":"","DDXLBJ":"","JXSM":"10000.0000","SF6QTEDYL":"0.6000","SF6QTBJYL":"0.5200","SF6QTBSYL":"0.5000","HZBSCZYL":"","FZBSCZYL":"","ZHZBSYL":"","ZDYXTZCS":"","EDSBKDDL":"","JQGZKDDL":"","EDXLCDKDDL":"","EDDLCDKDDL":"","EDLDCJNSDYDD":"","EDLDCJNSDYXJ":"","EDLDCJNSDYDK":"","YFZGPNYDD":"","YFZGPNYXJ":"","YFZGPNYDK":"","FZHLEDDYDY":"","DKXLBJ":"","CZJGEDCZDY":"","YZDX":"","YH":"","SF6QTZL":"","CNDJDY":"","CNSJ":"","QDYL":"","TZYL":"","HZJCBSCZYL":"","FZJCBSCZYL":"","ZHZBSJCCZYL":"","YCSGYL":"","YCJDYL":"","AQFDZYL":"","AQFDZFHYL":"","HZDZ":"","HZSJ":"55±8","FZSJ":"23±2","HFSJJSDJSJ":"30±10","SXFZBTQ":"","SXHZBTQ":"","TXFZBTQ":"","TXHZBTQ":"","RWDDL":"40.0000","DWDDL":"100.0000"} | 41311046430000000 | 2021-03-26 14:54:23 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | SF6气体湿度和纯度检测及密封性试验报告 | 305 | 断路器 | 交接 |  | 王志强，刘政 | D134260A-551B-451D-91C4-FBD63B1348EE-00010 | 国网湖南省电力公司 | 湖南省湘电试验研究院有限公司 | 湖南长沙宁乡500kV变电站 |  | 刘政 | 合格 | 归档 |  | 化学检测组 | 2021-12-01 00:00:00 | 2021-12-28 10:47:14 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 305 | 断路器 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变2L电抗器442断路器安装，设备质量无异常 | 归档 | 2021-12-28 09:29:56 | 66kVSF6瓷柱式断路器 | 4000A | 66kVSF6瓷柱式断路器,4000A,40kA,三相机械联动,户外 | 5 | 4000A | 72.5kVkV | 3AP1-FG | 西门子（杭州）高压开关有限公司 | 瓷柱式 | 20/K40044591
016010000000000026872139 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449665 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 220kV三相隔离开关,4000A,50kA,电动双柱水平伸缩,单接地 | 17002466 | G1010001 | 500004098 | 2 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000071 | 1 | 163130 | 1 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:19:32 | 91AR |  | 1901056887 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"SPOT-252/4000","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"Q311933002","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"252","EDDL":"4000.0000","EDPL":"50.0000","DWDDL":"125.0000","RWDDL":"50.0000","EDDSNSSJ":"5.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动并可手动","CZXS":"03","JGXSMC":"三相机械联动","JGXS":"01","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:19:32 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[Q311933002]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-10-10 00:00:00 | 2021-12-31 14:21:12 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变624B隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:47:16 | 220kV三相隔离开关 | 4000A | 220kV三相隔离开关,4000A,50kA,电动双柱水平伸缩,单接地 | 5 | 4000A | 252kV | SPOT-252/4000 | 阿尔斯通隔离开关（无锡）有限公司 | 三相机械联动 | Q311933002
016010000000000026872146 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449665 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 220kV三相隔离开关,4000A,50kA,电动双柱水平伸缩,单接地 | 17002466 | G1010001 | 500004098 | 2 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000071 | 1 | 163130 | 2 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:19:32 | 91AR |  | 1901056887 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"SPOT-252/4000","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"Q311933001","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"252","EDDL":"4000.0000","EDPL":"50.0000","DWDDL":"125.0000","RWDDL":"50.0000","EDDSNSSJ":"5.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动并可手动","CZXS":"03","JGXSMC":"三相机械联动","JGXS":"01","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:19:32 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[Q311933001]-电气-交接-2021-12-01 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D |  |  |  |  | 文轩 | 合格 | 编辑中 |  | 电气试验三队 | 2021-12-01 00:00:00 | 2021-12-30 21:14:30 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变614B隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:46:29 | 220kV三相隔离开关 | 4000A | 220kV三相隔离开关,4000A,50kA,电动双柱水平伸缩,单接地 | 5 | 4000A | 252kV | SPOT-252/4000 | 阿尔斯通隔离开关（无锡）有限公司 | 三相机械联动 | Q311933001
016010000000000026873389 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449647 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC220kV,50kA,电动 | 17002466 | G1010003 | 500007932 | 8 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000071 | 2 | 163229 | 1 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:13:39 | 91AR |  | 1901056888 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STA-252-50kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S311933008","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"252","EDDL":"4000.0000","EDPL":"50.0000","DWDDL":"125.0000","RWDDL":"50.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"三相机械联动","JGXS":"01","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:13:39 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S311933008]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-10-10 00:00:00 | 2022-01-02 15:26:25 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变620A2接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:50:55 | 交流接地开关 | AC220kV | 交流接地开关,AC220kV,50kA,电动 | 4 | 220kV | 252kV | STA-252-50kA | 阿尔斯通隔离开关（无锡）有限公司 | 三相机械联动 | S311933008
016010000000000026873396 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449647 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC220kV,50kA,电动 | 17002466 | G1010003 | 500007932 | 8 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000071 | 2 | 163229 | 2 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:12:48 | 91AR |  | 1901056888 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STA-252-50kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S311933007","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"252","EDDL":"4000.0000","EDPL":"50.0000","DWDDL":"125.0000","RWDDL":"50.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"三相机械联动","JGXS":"01","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:12:48 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S311933007]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-10-10 00:00:00 | 2022-01-02 15:30:19 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变620B2接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:51:56 | 交流接地开关 | AC220kV | 交流接地开关,AC220kV,50kA,电动 | 4 | 220kV | 252kV | STA-252-50kA | 阿尔斯通隔离开关（无锡）有限公司 | 三相机械联动 | S311933007
016010000000000026873402 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449647 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC220kV,50kA,电动 | 17002466 | G1010003 | 500007932 | 8 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000071 | 2 | 163229 | 3 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:12:11 | 91AR |  | 1901056888 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STA-252-50kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S311933006","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"252","EDDL":"4000.0000","EDPL":"50.0000","DWDDL":"125.0000","RWDDL":"50.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"三相机械联动","JGXS":"01","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:12:11 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S311933006]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-10-10 00:00:00 | 2022-01-02 15:21:27 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变610B2接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:49:40 | 交流接地开关 | AC220kV | 交流接地开关,AC220kV,50kA,电动 | 4 | 220kV | 252kV | STA-252-50kA | 阿尔斯通隔离开关（无锡）有限公司 | 三相机械联动 | S311933006
016010000000000026873419 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449647 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC220kV,50kA,电动 | 17002466 | G1010003 | 500007932 | 8 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000071 | 2 | 163229 | 4 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:11:25 | 91AR |  | 1901056888 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STA-252-50kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S311933005","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"252","EDDL":"4000.0000","EDPL":"50.0000","DWDDL":"125.0000","RWDDL":"50.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"三相机械联动","JGXS":"01","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:11:25 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S311933005]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-10-10 00:00:00 | 2022-01-02 15:28:32 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变620B1接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:51:27 | 交流接地开关 | AC220kV | 交流接地开关,AC220kV,50kA,电动 | 4 | 220kV | 252kV | STA-252-50kA | 阿尔斯通隔离开关（无锡）有限公司 | 三相机械联动 | S311933005
016010000000000026873426 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449647 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC220kV,50kA,电动 | 17002466 | G1010003 | 500007932 | 8 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000071 | 2 | 163229 | 5 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:10:44 | 91AR |  | 1901056888 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STA-252-50kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S311933004","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"252","EDDL":"4000.0000","EDPL":"50.0000","DWDDL":"125.0000","RWDDL":"50.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"三相机械联动","JGXS":"01","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:10:44 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S311933004]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-10-10 00:00:00 | 2022-01-02 15:24:04 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变620A1接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:50:18 | 交流接地开关 | AC220kV | 交流接地开关,AC220kV,50kA,电动 | 4 | 220kV | 252kV | STA-252-50kA | 阿尔斯通隔离开关（无锡）有限公司 | 三相机械联动 | S311933004
016010000000000026873433 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449647 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC220kV,50kA,电动 | 17002466 | G1010003 | 500007932 | 8 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000071 | 2 | 163229 | 6 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:10:00 | 91AR |  | 1901056888 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STA-252-50kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S311933003","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"252","EDDL":"4000.0000","EDPL":"50.0000","DWDDL":"125.0000","RWDDL":"50.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"三相机械联动","JGXS":"01","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:10:00 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S311933003]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-10-10 00:00:00 | 2022-01-02 14:25:55 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变610A1接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:48:03 | 交流接地开关 | AC220kV | 交流接地开关,AC220kV,50kA,电动 | 4 | 220kV | 252kV | STA-252-50kA | 阿尔斯通隔离开关（无锡）有限公司 | 三相机械联动 | S311933003
016010000000000026873440 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449647 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC220kV,50kA,电动 | 17002466 | G1010003 | 500007932 | 8 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000071 | 2 | 163229 | 7 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:09:22 | 91AR |  | 1901056888 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STA-252-50kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S311933002","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"252","EDDL":"4000.0000","EDPL":"50.0000","DWDDL":"125.0000","RWDDL":"50.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"三相机械联动","JGXS":"01","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:09:22 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S311933002]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 归档 |  | 电气试验三队 | 2021-10-10 00:00:00 | 2022-01-02 15:13:26 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变610B1接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:49:09 | 交流接地开关 | AC220kV | 交流接地开关,AC220kV,50kA,电动 | 4 | 220kV | 252kV | STA-252-50kA | 阿尔斯通隔离开关（无锡）有限公司 | 三相机械联动 | S311933002
016010000000000026873457 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449647 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC220kV,50kA,电动 | 17002466 | G1010003 | 500007932 | 8 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000071 | 2 | 163229 | 8 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:08:09 | 91AR |  | 1901056888 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STA-252-50kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S311933001","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"252","EDDL":"4000.0000","EDPL":"50.0000","DWDDL":"125.0000","RWDDL":"50.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"三相机械联动","JGXS":"01","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:08:09 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S311933001]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55E3635F922C905CA05E54B121015E55E361FC02C3 |  |  |  |  | 文轩 |  | 编辑中 |  | 电气试验三队 | 2021-10-10 14:29:34 | 2022-01-02 14:29:34 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变610A2接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:48:35 | 交流接地开关 | AC220kV | 交流接地开关,AC220kV,50kA,电动 | 4 | 220kV | 252kV | STA-252-50kA | 阿尔斯通隔离开关（无锡）有限公司 | 三相机械联动 | S311933001
016010000000000026873464 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449659 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC500kV,63kA,电动 | 17002466 | G1010003 | 500007936 | 4 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000072 | 1 | 163229 | 1 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:25:28 | 91AR |  | 1901056954 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STB-550-63kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S312027004","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"550","EDDL":"0.0000","EDPL":"50.0000","DWDDL":"60.0000","RWDDL":"63.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"单相操作","JGXS":"03","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:25:28 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S312027004]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 编辑中 |  | 电气试验三队 | 2021-10-10 00:00:00 | 2021-12-31 21:02:02 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变500kV母5117接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:53:33 | 交流接地开关 | AC500kV | 交流接地开关,AC500kV,63kA,电动 | 4 | 500kV | 550kV | STB-550-63kA | 阿尔斯通隔离开关（无锡）有限公司 | 单相操作 | S312027004
016010000000000026873471 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449659 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC500kV,63kA,电动 | 17002466 | G1010003 | 500007936 | 4 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000072 | 1 | 163229 | 2 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:24:39 | 91AR |  | 1901056954 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STB-550-63kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S312027003","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"550","EDDL":"0.0000","EDPL":"50.0000","DWDDL":"60.0000","RWDDL":"63.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"单相操作","JGXS":"03","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:24:39 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S312027003]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D |  |  |  |  | 文轩 |  | 编辑中 |  | 电气试验三队 | 2021-10-10 20:50:33 | 2021-12-31 20:50:33 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变500kV母5127接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:54:27 | 交流接地开关 | AC500kV | 交流接地开关,AC500kV,63kA,电动 | 4 | 500kV | 550kV | STB-550-63kA | 阿尔斯通隔离开关（无锡）有限公司 | 单相操作 | S312027003
016010000000000026873488 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449659 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC500kV,63kA,电动 | 17002466 | G1010003 | 500007936 | 4 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000072 | 1 | 163229 | 3 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:23:51 | 91AR |  | 1901056954 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STB-550-63kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S312027002","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"550","EDDL":"0.0000","EDPL":"50.0000","DWDDL":"60.0000","RWDDL":"63.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"单相操作","JGXS":"03","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:23:51 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S312027002]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 编辑中 |  | 电气试验三队 | 2021-10-10 00:00:00 | 2021-12-31 21:00:29 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变500kV母5217接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:55:17 | 交流接地开关 | AC500kV | 交流接地开关,AC500kV,63kA,电动 | 4 | 500kV | 550kV | STB-550-63kA | 阿尔斯通隔离开关（无锡）有限公司 | 单相操作 | S312027002
016010000000000026873495 | 隔离开关 | 140300015 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 6449659 | 省公司统购WBS | 1316A01900PS04 | 省公司统购WBS | 交流接地开关,AC500kV,63kA,电动 | 17002466 | G1010003 | 500007936 | 4 | 国网湖南电力集中采购工厂 | 阿尔斯通隔离开关（无锡）有限公司 | X | 主设备 | 1000 | 20200827 | HN20200000072 | 1 | 163229 | 4 | SG2003 | 1 | 已提报 | 隔离开关 | 隔离开关 | 2021-03-26 14:23:09 | 91AR |  | 1901056954 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 隔离开关 | 140300015 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 1 | {"XH":"STB-550-63kA","SCCJMC":"阿尔斯通隔离开关（无锡）有限公司","SCCJ":"000006","CCBH":"S312027001","CCRQ":"20201125","CPDH":"","ZZGJMC":"","ZZGJ":"","JDKGXH":"","DJZL":"","JDKGKHGYDLNLMC":"","JDKGKHGYDLNL":"","EDDY":"550","EDDL":"0.0000","EDPL":"50.0000","DWDDL":"60.0000","RWDDL":"63.0000","EDDSNSSJ":"3.0000","DXHSXJGMC":"三相","DXHSXJG":"02","CZXSMC":"电动","CZXS":"02","JGXSMC":"单相操作","JGXS":"03","JDKGJGXSMC":"","JDKGJGXS":"","JDKGRWDDL":"","JDKGCZXSMC":"","JDKGCZXS":"","JDKGXSMC":"","JDKGXS":"","GWLXMC":"","GWLX":"","LDCJNYFZDD":"","LDCJNYFZDK":"","CDDJGZDYLBMC":"","CDDJGZDYLB":"","CDDJKZDYLBMC":"","CDDJKZDYLB":"","JDDJGDJXH":"","JDDDJGZDYLBMC":"","JDDDJGZDYLB":"","JDDDJKZDYLBMC":"","JDDDJKZDYLB":"","JDDZPZMC":"","JDDZPZ":"","ZHLDZ":""} | 41311046430000000 | 2021-03-26 14:23:09 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 湖南长沙宁乡500kV输变电工程-隔离开关[S312027001]-电气-交接-2021-10-10 | 306 | 隔离开关 | 交接 |  | 匡成，文轩 | 55DC2BA3812C905CA05E54B121015E55DC2A53029D | 国网湖南省电力有限公司 | 湖南省送变电工程有限公司 | 500kV安宁站 |  | 文轩 | 合格 | 编辑中 |  | 电气试验三队 | 2021-10-10 00:00:00 | 2021-12-31 20:58:33 | 1316A01900PS | 湖南长沙宁乡500kV输变电工程 | 1316A01900PS04 | 宁乡500kV变电站新建工程 | 306 | 隔离开关 | 安装 | 张铁武 | 彭胜华、严民、杨亚林等 | 金吉发 | 安宁变500kV母5227接地隔离开关安装，设备质量无异常 | 归档 | 2021-12-28 09:56:00 | 交流接地开关 | AC500kV | 交流接地开关,AC500kV,63kA,电动 | 4 | 500kV | 550kV | STB-550-63kA | 阿尔斯通隔离开关（无锡）有限公司 | 单相操作 | S312027001